## Slide 1: EASIcab Kick-off Meeting
PRESENTED In house
Date : 29th July 2016

## Slide 2: AGENDA
Customer profile
Project Scope
Project Description
Customer requirements
Project Flow Diagram
Customer supplied material
Project Execution approach
Project plan
Resource plan [Hardware / Software / People etc.]
Communication plan
Quality requirements
Assumptions
Risk Management
Change Management
Project Deliverables
How to use

## Slide 3: Customer Profile
Name: EASi engineering Travel Desk
Location: India
Overview about customer products / business:
      EASi provides critical, innovative engineering solutions around the globe for customer as well as employees.
      EASi Cab management system plays a vital role for employee in point of safe & secure transportation.

## Slide 4: Project Scope
Simple and easy smart phone application to monitor and manage the EASi cab facilities
Easily manage the cab facilities by smartphones
The project entails:
Develop smartphone applications(android) for easy and safety management
Web Service development for the whole app module
Integrate the application with web services

## Slide 5: Project Overview

## Slide 6: Development Approach
Phase 1:
Static flow between all screens in android application.
Simple Google map integration with current location.
Phase 2.1:
UI for three different role ( Admin, Driver, Employee) with supporting multiple screen sizes
Log in, Registration, settings and Check-in and Check-out functionalities
Cab monitoring & Google map
Call and SMS service
SOS (Emergency Button)
Web service Integration in the application
Export reports in excel format
Phase 2.2:
Voice recognition module
Note: It’s a separate module , If success it can be combined in the application

## Slide 7: Project Description
Phase 3:
Tracking with real GPS device.
Notification
Publishing the application to cloud

## Slide 8: Block diagram

## Slide 9: Customer Requirements
UI :
UI for different role based app modules e.g. Driver, Employee and Admin for smartphone supporting all screen sizes
Functionalities :
UI for three different role ( Admin, Driver, Employee) with supporting multiple screen sizes
Log in, Registration, settings and Check-in and Check-out functionalities
Cab monitoring & Google map
Call and SMS service
SOS (Emergency Button)
Web service Integration in the application
Export reports in excel format

## Slide 10: Project Flow

## Slide 11: Customer Supplied Material
Provided :
Android & iOS devices for testing
Credential for SVN
Requirement document
Request to provide :
  iOS developer credentials
R&D required :
  Web services in java
  Voice recognition module

## Slide 12: Project Execution Approach
Planning
    Requirement gathering
    Create UI/UX design flow & document
    Create effort estimation of version 1 & 2
    Create and submit Project Proposal
    Study of requirements spec
    Code development
    Manual test plan for new functionality
    Perform static analysis of code
    Create Checklist for internal review
    Create user manual guide
Execution
    Create Review log for all files
    Internal review and approval of all work products
Review and approval
Acceptance & Closure
    Project acceptance signoff

## Slide 13: Project Plan
Milestone | Date
Project Kick-off (Internal) | 29-july-2016
Project Kick-off | 
Project start date | 
User manual | 
Code development | On-going through the project execution phase
Review | On-going through the project execution phase
Test Report | On-going through the project execution phase

## Slide 14: Resource Plan [Software / Hardware / People]
Tool & Software :
Android Studio – Android Development
X-code – iOS Development
Eclipse, Apache
Tomcat Server &
MySQL Database – Web Service Development
SVN -- Source control
Simulator – For application Testing
Testing Tool- Bugzilla
Programming Languages :
Java (Web Service & Android)
Swift (iOS)
Hardware
Android devices
iOS devices
Resource
Android Developer engineer – Subhalaxmi, Nitesh
iOS Developer engineer - Rohit

## Slide 15: Communication Plan
Deliverables shall be sent via SVN source control
Weekly status update will be maintained in team.
Queries and responses will be collated on a query tracker and updated to SVN on a daily basis, if any
All status, MOMs and required documents need to be maintained in SVN.

## Slide 16: Quality Requirements
Minimum 95% FTR and 90% OTD have to be achieved and all work products shall be stored in SVN
Benchmark target is (+/-) 10%
Internal review of all work products shall take place and be maintained in SVN
Review checklist shall be used for all Internal reviews
Weekly quality metrics shall be maintained and published
All communication in team or with manager will be maintained in SVN

## Slide 17: Assumptions
Phase 1 :
We will work on the local database(android preferences) inside mobile till web service is ready
It will be the static flow for basic demo purpose
Phase 2 :
For iOS mobile application, we’ll be using the simulator for debugging, as we don’t have the apple developer membership (account) for profiles and certificates for testing in the real device
Phase 3 :
Publish web service and MySQL Database

## Slide 18: Risk Management
Risk Description | Probability of Occurrence | Impact | Mitigation Plan | Contingency Plan
If any Resource is absent due to emergency, it may hamper the deliverables | Medium | Medium | NA | Back up Resource will be used. Internal Training/KT in team
iOS developer account | Medium | High | We will test in simulator. | Try to apply it in later version.

## Slide 19: Change Management
Any functionality or activities that are not specifically mentioned in the scope are considered excluded from the scope of this proposal. If EasiCab so requires, such functionalities or activities can be considered as a change of scope and routed through EASi’s Change Management Process as illustrated.

## Slide 20: Change Management
Receive Change Request (CR)
Register CR in CR Log with CR Priority and Status: Open
Perform CR Impact Analysis
Estimate effort and cost
Estimate impact on schedule, if any
Check for additional specifications, if required
Communicate CR Impact to Customer
Estimate effort and cost
Estimate impact on schedule, if any
Request additional specifications, if required
Update Impacted activity and work products (including Specifications, if any)
Communicate to CR Stakeholders
Execute Change Request
Log the CR activity as a New Task
Update the necessary revision details / attributes for the impacted change and functionality
Update CR Log with CR Status: Closed
Update CR Log with CR Status: Dropped
Seek Approval from Customer CRequestor
Yes
Amend SOW / PO to Incorporate CR
No

## Slide 21: Project Deliverables
Working Code (UI/Functionalities)
.apk file of android
.ipa file of iOS
User manual
Note: All project reports, documents and source code will available in SVN Path:
https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/

## Slide 22: How to use

## Slide 23: How it will work..

## Slide 24: Thank you
For more details, please contact:
EASi Embedded
Bangalore