## Slide 1: Project Kick-off Meeting
Project Name: iPlanter Date: 21-August-2015

## Slide 2: Agenda
Customer profile
Project Scope
Project Description
Customer requirements
Customer supplied material
Project Execution approach
Project plan
Resource plan [Hardware / Software / People etc.]
Communication plan
Quality requirements
Assumptions
Risk Management
Change Management
Project Governance and Escalation Mechanism
Project Deliverables

## Slide 3: Customer Profile
Name: CNHi
Location: USA
Overview about customer products / business:
      CNH Industrial is one of the world's largest capital goods companies registered in the Netherlands with corporate offices in London. Through its various businesses designs, produces, and sells agricultural equipment and construction equipment (Case and New Holland brand families), trucks, commercial vehicles, buses, and special vehicles (Iveco), in addition to powertrains for industrial and marine applications.

## Slide 4: Project Scope
The project entails:
  Android application development. (UI/ Functionalities)
  Communicate with Planter in term of Signal.
  Manual testing.
  Static analysis (review) of the entire code.

## Slide 5: Project Description
Control and perform various operations in planters using Hand-Held device. The bi-directional communication between planter and application is based on Google proto-buf through Wi-Fi . In addition to that, manual testing for the Signal functionality is to be performed. A Static analysis of the entire code against previously applied coding standards will also be performed.

## Slide 6: Customer Requirements
Develop UI for Hand-Held device.
Develop required functionality to communicate with Planter
Manual test Report

## Slide 7: Customer Supplied Material
Provided
External communicator board for Signal(Request & Response)
LAN wire
Latest version of source code
Android 10 inch tablet
Credential for Git repo
Requirement document
Latest Functional requirement
Request to provide
  Credential for others libraries

## Slide 8: Project Execution Approach
Planning
    Study of code
    Creation of SOW
    Create effort estimation
    Create and submit Project Proposal
    Review of Milestones and Risk tracker
    Study the code and requirements spec
    Code development
    Manual test plan for new functionality
    Perform static analysis of code
    Perform manual test
    Create Checklist for internal review
    Create defect logs
Execution
    Create Review log for all files.
    Internal review and approval of all work products
Review and approval
Acceptance & Closure
    Project acceptance signoff
Legend:
EASi actions
iPlanter action

## Slide 9: Project Plan
Milestone | Date
Project Kick-off | 21-Aug-2015
Project start date | 15-Sept-2015
Issues /Bug found | On-going through the project execution phase
SW Code review report | On-going through the project execution phase
Manual Test Report | On-going through the project execution phase

## Slide 10: Resource Plan [Software / Hardware / People]
Software
IntelliJ IDEA
Git
Maven
Hardware
Circuit board
LAN Wire
Net gear Router
10 inch Android tablet
People
Delivery Manager – Pramad Nallari
Practice Solution Manager – Pramad Nallari
On-site coordinator– Kurt, US
Delivery Manager – Deepa Shastry, India
Team Lead – Jayachandran , India
Developer engineer – Subhalaxmi, Dilshad, Nitesh, India
Buffer resource – Anusha, Sudam, India

## Slide 11: Communication Plan
Deliverables shall be sent via Git version control
Daily status update will be sent by coordinator of team to Client
Queries and responses will be collated on a query tracker and updated on a daily basis if any
Weekly status meetings including the Delivery Managers and iPlanter management and technical teams

## Slide 12: Quality Requirements
Minimum 95% FTR and 90% OTD we have to achieve and all work products shall be stored in SVN.
Benchmark target is (+/-) 10%
Internal review of all work products shall take place and be maintained in SVN.
Review checklist shall be used for all Internal reviews.
Weekly quality metrics shall be maintained and published.
All communication with CNHi will be maintained in SVN.

## Slide 13: Assumptions
We don’t have real planter with us, still we have to write code in such a way , so that it will work.
For testing , if required we need to develop a Simulator for Signal communication.
For database we will use Shared preference as temporary data base.
iPlanter resources will be available during the KT of the project
Project Start is considered to be after all parts, documents and code are received at the Design Center

## Slide 14: Risk Management
Risk Description | Probability of Occurrence | Impact | Mitigation Plan | Contingency Plan
Skill set mismatch(Project preferred skill set) | Low | High | Skill set mismatch will be raise to PM | 
If any Resource is absent due to emergency, it may hamper the deliverables | Medium | Medium | NA | Back up Resource will be used
Delay in response regarding issue | Medium | High | We will do follow-up and move to next task. | Work out an intermediate plan of what work can still progress
Communication gap- Team is not able to explain technical issue to onsite coordinator. | Low | High | We will try to arrange WebX meeting and will explain through mail. | 

## Slide 15: Change Management
Any functionality or activities that are not specifically mentioned in the scope are considered excluded from the scope of this proposal. If iPlanter so requires, such functionalities or activities can be considered as a change of scope and routed through EASi’s Change Management Process as illustrated.
Receive Change Request (CR)
Register CR in CR Log with CR Priority and Status: Open
Perform CR Impact Analysis
Estimate effort and cost
Estimate impact on schedule, if any
Check for additional specifications, if required
Communicate CR Impact to Customer
Estimate effort and cost
Estimate impact on schedule, if any
Request additional specifications, if required
Update Impacted activity and work products (including Specifications, if any)
Communicate to CR Stakeholders
Execute Change Request
Log the CR activity as a New Task
Update the necessary revision details / attributes for the impacted change and functionality
Update CR Log with CR Status: Closed
Update CR Log with CR Status: Dropped
Seek Approval from Customer CRequestor
Yes
No
Amend SOW / PO to Incorporate CR

## Slide 16: Project Governance & Escalation Mechanism
Deepa Shastry,India | OPERATIONAL COUNCIL | 
 | Meeting: Once a Week Project Status & Tracking, KPIs / SLAs Tracking, Operation Issues, Delivery Coordination, Issue Consolidation & Tracking, Project Level Risk Management; | 
Kurt, US | STEERING COMMITTEE | 
 | Meeting: Once a Quarter Goal Definition, Strategy Planning, Quarterly Progress Review, | 
Pramad Nallari, US | RELATIONSHIP COUNCIL | 
 | Meeting: If required Implement Strategies, Monitor KPIs, Escalated Issue Resolution, Engagement Assessment | 
EASi Leadership Team
Delivery Manager
Project Manager / Team Lead
iPlanter/ Engineering Team
iPlanter engineering Manager / SPOC
iPlanter Leadership Team
Escalation

## Slide 17: Project Deliverables
Working Code (UI/Functionalities)
Manual test report

## Slide 18
Thank you!
Questions?
www.easi.com
www.aerotek.com
www.allegisgroup.com
INDIA
24, Salarpuria Arena,
6th Floor Hosur Main Road, Adugodi,
Bangalore- 560030
India
Phone: +91 80 3070 5102
Fax: +91 80 2841 3299
Notes: Spruce up this slide:
EASi is a market leader in providing engineering support services and technology solutions for the global market. Established in 1981, EASi is headquartered in Hanover, MD with engineering centers in the US and India. We offer comprehensive and innovative solutions covering Virtual Product Development, Systems Engineering and Manufacturing Engineering for our customers.
As a strategic engineering partner to many global Fortune 500 companies, EASi’s legacy of global engineering support services and consulting experience spans more than 30 years.
EASi is a subsidiary of Aerotek, a leader in the recruiting and staffing industry. Founded in 1983, Aerotek provides technical, professional and industrial staffing solutions to variety of industries. Aerotek is an operating company of Allegis Group® Inc., the largest staffing company in the US.