## INTRODUCTION
ESTIMATION
TASK_STATUS
TIMELINE
TEAM STRUCTURE
REVIEW LOGS
METRICS
CAPA STATUS
MOM
RISK REGISTER
HARDWARE INVENTORY LIST
MILESTONES
STATUS MEETING
QUERY LIST
LESSONS LEARNT
ISSUES FOUND
FTR DEFINITION
DELIVERABLES
ESTIMATE SUMMARY
PED DOCUMENT
TRACEBALITY MATRIX
TEST PLAN
Note on B9: Author: Click on to open the respective file names.
EASi Cab

## TASK_STATUS
TASK STATUS
S.NO | FILE NAME | METHOD NAME | CYCLOMATIC COMPLEXITY | CODING START DATE | TASK COMPLETED DATE | ESTIMATED TIME CASE CREATION [HRS] | ACTUAL TIME [HRS] | AUTHOR | INTERNAL REWORK [HRS] | INTERNAL FTR | EXTERNAL REWORK [HRS] | EXTERNAL FTR | REVIEWER | ACTUAL 1st REVIEW HOURS | ESTIMATED 1st REVIEW HOURS | ESTIMATED 2nd REVIEW HOURS | ACTUAL 2nd REVIEW HOURS | REVIEWER STATUS | DELIVERED TO CUSTOMER
Note on E2: Author: Mention the start date when you create the test case.
Note on F2: Author: Mention the test case delivery date.
Note on H2: Author: Note the time taken for the test case creation.
Note on J2: Author: Mention the time taken for internal reworks reviewed by peer reviewer.
Note on K2: Author: This column is to mention the work product delivered is FTR[First time right].
Note on L2: Author: Mention the time taken for external reworks reviewed by customer.
Note on M2: Author: The External FTR is the work product[WP] has delivered to the customer and its been accepted. TEAM PERCEPTION -If you have delivered the WP to customer.Select this[Assuming delivered is correct]
Note on O2: Author: Actual time taken to Review
Note on P2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on Q2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on R2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on S2: Author: Internal reviewer has to update the status regarding the reviewed WP.
Note on T2: Author: Delivered the particular work product to the customer.

## ESTIMATED_TIMELINE
ESTIMATED TIMELINE | [14 empty] | HOLIDAY |  |  |  | TEST CASE CREATION | [5 empty] | Resource Leave
[15 empty] | EXECUTION |  |  |  | REVIEW
[15 empty] | COMPLETED |  |  |  | SYSTEM TESTING
FILE NAME | ESTIMATED Time Planning & designining [HRS] [HRS] | ESTIMATED Time for documentaion [HRS] | ESTIMATED Time for UI[HRS] | ESTIMATED Time for Functionalities[HRS] | ESTIMATED Time for integration of UI & Functionalities[HRS] | FIRST REVIEW HOURS | SECOND REVIEW HOURS | Rework hours | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28
Project Kick Off | bar: 2016-07-30 to 2016-07-31
| Abilash | 4 | 108.75
| Arun | 4 | 32.5
| Mamatha | 3 | 42
| Punith | 4 | 115
| Ramesh | 4 | 92
| Sai | 3 | 55
Note on G5: Author: 1st Review hours = Estimated time for test case creation *(1/3)
Note on H5: Author: 2nd level review hours = First review hours /2

## ACTUAL_TIMELINE
ACTUAL TIMELINE | [11 empty] | HOLIDAY |  |  |  | TEST CASE CREATION | [5 empty] | RESOURCE LEAVE
[12 empty] | EXECUTION |  |  |  | REVIEW | [5 empty] | SECOND REVIEW
[12 empty] | COMPLETED |  |  |  | SYSTEM TESTING | [5 empty] | REPORT PREPARATION
FILE NAME | ESTIMATED Time Planning & designining [HRS] [HRS] | ESTIMATED Time for documentaion [HRS] | ESTIMATED Time for UI[HRS] | ESTIMATED Time for Functionalities[HRS] | ESTIMATED Time for integration of UI & Functionalities[HRS] | FIRST REVIEW HOURS | SECOND REVIEW HOURS | Rework hours | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28
Internal Project Kick Off | bar: 2016-07-30 to 2016-07-31; 2016-08-06 to 2016-08-07; 2016-08-14 to 2016-08-15; 2016-08-20 to 2016-08-21; 2016-08-27 to 2016-08-28
Design Documentaion | bar: 2016-07-30 to 2016-07-31; 2016-08-06 to 2016-08-07; 2016-08-14 to 2016-08-15; 2016-08-20 to 2016-08-21; 2016-08-27 to 2016-08-28
Database Documentaion | bar: 2016-07-30 to 2016-07-31; 2016-08-06 to 2016-08-07; 2016-08-14 to 2016-08-15; 2016-08-20 to 2016-08-21; 2016-08-27 to 2016-08-28
Note on G5: Author: 1st Review hours = Estimated time for test case creation *(1/3)
Note on H5: Author: 2nd level review hours = First review hours /2

## TEAM_STRUCTURE
EmployeeCode | EmployeeName | 16-August-2016 to 21-August-2016
|  | Week No | Week No | Week No | Week No | Week No | Week No | Week No | Week No
4335 | Subhalaxmi Nayak
4463 | Nitesh Kumar
Rohit Soraf
Billable hours |  | HRS |  | Billable
Engineer 1 | Subhalaxmi | 0 |  | Buffer
Engineer 2 | Nitesh | 0
Engineer 3 | Rohit | 0
Engineer 4
Total Engineer week hours |  | #NAME?
TOTAL EFFORT | Hours
3 Engineer | 0
Note on C6: Green colour indicates resource worked on weekends.

## REVIEW_LOGS
REVIEWS LOG
S.NO | REVIEW LOG
1 | Database Document
2 | Design Document
3 | SplashScreen.java
4 | LoginScreen.java
Note on B5: Author: For review logs click on respective file name.

## METRICS
METRICS & TIME SHEET TRACKER
S.NO | TIME SHEET WEEK NO | METRICS WEEK NO
1
2
3
4
5
6
7
8
Note on B5: Author: click on time sheet column for respective time sheet week.
Note on C5: Author: click on Metrics week no column for respective metrics week.

## CAPA
CAPA TRACKER
S.NO | CAPA WEEK
1 | CAPA WEEK NO
Note on B4: Author: Mention which week CAPA has been raised.Click on the link to open the document.
Note on B5: Author: This is CAPA template

## MOM
MOM TRACKER
S.NO | DATE | MEETING
1 | 2016-07-29 | Internal_Kickoff_Meeting
2
Note on C5: Author: Click on the respective meeting for MOM.

## FTR_DEFINITION
FTR DEFINITIONS OF Phase 1 EASiCab
Per 100 LOC or Per 100 Test Cases
FTR %age | 100 | 95 | 90 | 80 | 75 | 0
Critical | 0 | 0 | 0 | 0 | 0 | 1
Major | 0 | 0 | 0 | 1 | upto 5 | >6
Medium | 1 | 5 | 5 to 10 | 10 to 15 | 15 to 25 | >26
Minor | upto 5 | 5 to 15 | 15 to 25 | 25 to 35 | 35 to 50 | >51
Category | Description
Critical | [1].Application is not secuired.
[2]. On installation of the app, it will Crash, Hang or affect the device full operating system. It may need to re-flashing the OS.
[3].Viruse found and affect other devices.
Major | [1].If application is crashing without any notification i.e. ANR
[2].Unexpected application behaviour. i.e. Opening page not as per expected.
[3]. No error handling, No required notification, No network handling or notification for user
[4]. Data mismatch. i.e. Details are not coming as per login user.
Medium | [1].No vallidation for entry fields i.e email, password or empty entries.
[2]. Not supporting all screen sizes. Positioning of views is not constant.
[3].Unexpected application behaviour in perticular devices.
Minor | [1] UI component sizes mis-match
[2].Text color/size/font mismatch. Text of views mismatch.
Note on B12: Author:
Note on B14: Author: On installation, it may affect full operating system.
Note on B18: Author:
Note on B20: Author: On clicking of submit button in login page leads to register page instead of home page
Note on B22: Author:
Note on B24: Author: The details displayed is not as per the login user. On success full login, the details are available are of other user (not loginuser). Expected result not available as per valid user.
Note on B26: Author:
Note on B28: Author:
Note on B30: Author: Same piece of code not working in few devices(any) or showing ANR in perticular device/version. It may be secuirity permission issues or device theme issues
Note on B32: Author: Icon size mismatch from recuired documents
Note on B34: Author: Textv color, text size , text string are differing.Spelling mistake, positioning or spacing between text etc.

## DELIVERABLES
DELIVERABLES
SOURCE CODE
MANUAL GUIDE
.apk files
.ipa files

## ESTIMATE_SUMMARY
ACTUAL VS ESTIMATED SUMMARY
Version 1
ESTIMATED TIME |  | ACTUAL TIME |  | TOTAL ESTIMATED TIME V1 |  | TOTAL ESTIMATED TIME V2
[5 empty] | Hours |  | Hours
UI ESTIMATED | HOURS | UI ACTUAL | HOURS | UI Development |  | UI Development
Estimated UI development (hrs) |  | Actual UI development (hrs) |  | Functionality Development |  | Functionality Development
Estimated UI development testing(multiple screen) before submitting to review (hrs) |  | Actual UI development testing(multiple screen) before submitting to review (hrs) |  | Integration of UI andFunctionality Development |  | Integration of UI andFunctionality Development
Estimated 1st review (hrs) |  | Actual 1st review (hrs) |  | Total | 0 | Total
Estimated 2nd review (hrs) |  | Actual 2nd review (hrs)
Internal rework (hrs) |  | Internal rework (hrs)
External rework (hrs) |  | External rework (hrs) |  | TOTAL ACTUAL TIME
Estimated time for report preparation |  | Actual time for report preparation |  |  | Hours
Estimated total |  | Actual total |  | UI Development
UI Development
Integration of UI andFunctionality Development
FUNCTIONALITIES ESTIMATED | HOURS | FUNCTIONALITIES ACTUAL | HOURS | Total | 0
Estimated for functionalities development (hrs) |  | Actual time for for functionalities development (hrs)
Estimated time for integrating functionalities and UI development (hrs) |  | Actual time for integrating functionalities and UI development (hrs)
Estimated time for internal testing before submitting to review (hrs) |  | Actual time for internal testing before submitting to review (hrs)
Estimated review hours |  | Actual review hours
Estimated time for Report preparation |  | Actual time for Report preparation
External rework
ESTIMATED TOTAL |  | ACTUAL TOTAL
Note on M5: Author: This Estimate was sent to customer for V4.19
Note on Q5: Author: This Estimate for V4.22.
Note on B8: Author: Estimated time for v4.19 1st sent to customer = 437hrs Changed estimate V4.22 = 440.75 hrs
Note on B9: Author: Estimated time for v4.19 1st sent to customer = 457hrs Changed estimate V4.22 = 437hrs
Note on T9: Author: Two layers of review added in new estimate
Note on B14: Author: Estimated time for v4.19 1st sent to customer = 91.4hrs Changed estimate V4.22 = 87.4hrs
Note on B15: Author: Total Estimated time for UTC v4.19 1st sent to customer excluding the 1st and 2nd review hours = 985.95hrs Changed estimate V4.22 including 1st and 2nd review hours =1093.13 hrs