## Slide 1: EASicab Kick-off Meeting
PRESENTED In house
Date : 18th August 2016

## Slide 2: AGENDA
Customer profile
Project Scope
Project Overview
Development approach
Block Diagram
Customer requirements
Project Flow Diagram
Customer supplied material
Project Execution approach
Project plan
Resource plan [Hardware / Software / People etc.]
Communication plan
Quality requirements
Assumptions
Risk Management
Project Deliverables
How to use & How it will work

## Slide 3: Customer Profile
Name: EASi Engineering Travel Desk
Location: Bangalore, India
Overview about customer products / business:
      EASi Engineering Travel Desk provides cab facility for employees who work in the night shift considering employee safety.

## Slide 4: Project Scope
Simple and user friendly smart phone application to monitor and manage the EASi cab facilities.
The project entails:
Develop smartphone applications(android)
Web Service development

## Slide 5: Project Overview

## Slide 6: Development Approach
Phase 1: UI
Static flow between all screens in android application.
UI for three different role ( Admin, Driver, Employee) with supporting multiple screen sizes
Google map integration with current location.
Phase 2: Functionality Implementation
2.1:
Log in, Registration, settings and Check-in and Check-out functionalities
Cab monitoring & Google map
Call and SMS service
SOS (Emergency Button)
Web service Integration in the application
Export reports in excel format
2.2:
Voice recognition module

## Slide 7: Development Approach
Phase 3:
Notification
Tracking with real GPS device.
Publishing the application to Play store

## Slide 8: Block diagram

## Slide 9: Customer Requirements
UI :
UI for different role based app modules e.g. Driver, Employee and Admin for smartphone supporting all screen sizes
Functionalities :
UI for three different role ( Admin, Driver, Employee) with supporting multiple screen sizes
Log in, Registration, settings and Check-in and Check-out functionalities
Cab/Employee monitoring & Google map
Call and SMS service
SOS (Emergency Button)
Web service Development
Web service Integration in the application
Export reports in excel format

## Slide 10: Project Flow

## Slide 11: Customer Supplied Material
Provided :
Android devices for testing
Credential for SVN
Requirement document
Requested to Provide:
Google play store account

## Slide 12: Project Execution Approach
Planning
    Requirement gathering
    Create UI/UX design flow & document
    Create effort estimation of version 1 & 2
    Create and submit Project Proposal
    Study of requirements spec
    Code development
    Manual test plan for new functionality
    Perform static analysis of code
    Create Checklist for internal review
    Create user manual guide
Execution
    Create Review log for all files
    Internal review and approval of all work products
Review and approval
Acceptance & Closure
    Project acceptance signoff

## Slide 13: Project Plan
Milestone | Date
Project Kick-off (Internal) | 29-july-2016
Project Kick-off | 18-August-2016
Project start date | 23-August-2016
User manual | End of the Project
Code development | On-going through the project execution phase
Review | On-going through the project execution phase
Test Report | On-going through the project execution phase

## Slide 14: Resource Plan [Software / Hardware / People]
Tool & Software :
Android Studio – Android Development
Eclipse, Apache Tomcat Server
& MySQL Database – Web Service Development
SVN -- Source control
Simulator – For application Testing
Testing Tool-- Bugzilla
Programming Languages :
Java (Web Service & Android)
Hardware
Android devices
Resource
Android Developer – Subhalaxmi, Nitesh
Web service Developer -- Rohit

## Slide 15: Communication Plan
Deliverables shall be sent via SVN source control
Weekly status update will be maintained with in team.
Queries and responses will be collated on a query tracker and updated to SVN on a daily basis, if any
All status, MOMs and required documents need to be maintained in SVN.

## Slide 16: Quality Requirements
Minimum 85% FTR and 90% OTD have to be achieved and all work products shall be stored in SVN
Benchmark target is (+/-) 10%
Internal review of all work products shall take place and be maintained in SVN
Review checklist shall be used for all Internal reviews
All communication in team or with manager will be maintained in SVN

## Slide 17: Assumptions
Phase 1 :
We will work on the local database(android preferences) inside mobile till web service is ready
It will be the static flow for basic demo purpose
Phase 2 :
Tracking with the mobile GPS not with real GPS module

## Slide 18: Risk Management
Risk Description | Probability of Occurrence | Impact | Mitigation Plan | Contingency Plan
If any Resource is absent due to emergency, it may hamper the deliverables | Medium | Medium | NA | Extra effort need to put or. Internal Training/KT in team so that buffer resource can be used
Android play store account | Medium | High | NA | Requested to provide

## Slide 19: Project Deliverables
Working Code (UI/Functionalities)
.apk file of android
User manual
Note: All project reports, documents and source code will available in SVN Path:
https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/

## Slide 20: How to use

## Slide 21: How it will work..

## Slide 22: Thank you
For more details, please contact:
EASi Embedded
Bangalore