## Slide 1: EASIcab Kick-off Meeting
PRESENTED In house
Date : 29th July 2016

## Slide 2: AGENDA
Customer profile
Project Scope
Project Description
Customer requirements
Project Flow Diagram
Customer supplied material
Project Execution approach
Project plan
Resource plan [Hardware / Software / People etc.]
Communication plan
Quality requirements
Assumptions
Risk Management
Change Management
Project Deliverables
How to use

## Slide 3: Customer Profile
Name: EASi engineering (In-house)
Location: India
Overview about customer products / business:
      EASi provides critical, innovative engineering solutions around the globe. Unparalleled ability to build specialized teams of world-class experts, leveraging cutting-edge technology, training and processes, allows EASi to constantly improve and innovate to deliver as per customers need.

## Slide 4: Project Scope
The project entails:
  Android & iOS application development. (UI/ Functionalities)
  Call and SMS
  SOS and Camera
  Live tracking
  Manual testing
  Web services
  Voice recognition

## Slide 5: Project Scope

## Slide 6: Project Description
Simple and easy smart phone application to control the EASi cab facilities.
Easily manage the cab facilities by smartphones.
Module 1: (Demo)
Static flow between all screens in android application.
Simple Google map integration with current location.
Module 2: (Local Services)
UI for three different role ( Admin, Driver, Employee) with supporting multiple screen sizes
Log in, Registration, settings and Check-in and Check-out functionalities
Live tracking and Google map
Call and SMS service
SOS (Emergency Button)
Voice recognition integration (R&D)

## Slide 7: Project Description
Module 3: (Global)
Web service Integration in the application.
Tracking with real GPS device.
Push Notification
Export reports in excel format

## Slide 8: Customer Requirements
UI :
UI for different role based app modules e.g. Driver, Employee and Admin for smartphone supporting all screen sizes as per UI/UX doc.
Check Web URL:
https://projects.invisionapp.com/d/login
Functionalities :
Develop required functionality far easy and safety management for the different role based modules e.g. Driver, Employee & Admin
Web Service development for the whole app module
Web Service integration with the mobile app
Manual test Reports

## Slide 9: Project Flow

## Slide 10: Customer Supplied Material
Provided :
Requirement UI/UX flow
Android devices for testing
Credential for SVN
Requirement document
Request to provide :
  iOS developer credentials
R&D required :
  Web services in java
  Voice recognition module

## Slide 11: Project Execution Approach
Planning
    Study of code
    Create effort estimation
    Create and submit Project Proposal
    Review of Milestones and Risk tracker
    Study the code and requirements spec
    Code development
    Manual test plan for new functionality
    Perform static analysis of code
    Perform manual test
    Create Checklist for internal review
    Create defect logs
Execution
    Create Review log for all files.
    Internal review and approval of all work products
Review and approval
Acceptance & Closure
    Project acceptance signoff

## Slide 12: Project Plan
Milestone | Date
Project Kick-off | 29-july-2016
Project start date | 03-August-2016
Issues /Bug found | On-going through the project execution phase
SW Code review report | On-going through the project execution phase
Manual Test Report | On-going through the project execution phase

## Slide 13: Resource Plan [Software / Hardware / People]
Tool & Software :
Android Studio – Android Development
X-code – iOS Development
Eclipse, Apache
Tomcat Server &
MySQL Database – Web Service Development
SVN -- Source control
Simulator – For application Testing
Programming Languages :
Java (Web Service & Android)
Swift (iOS)
Hardware
Android devices
Resource
Manager – Deepa Shastry
Android Developer engineer – Subhalaxmi, Dilshad, Nitesh, India
iOS Developer engineer - Nagarjun, Rohit

## Slide 14: Communication Plan
Deliverables shall be sent via SVN source control
Weekly status update will be maintained in team.
Queries and responses will be collated on a query tracker and updated to SVN on a daily basis, if any
All status, MOMs and required documents need to be maintained in SVN.

## Slide 15: Quality Requirements
Minimum 95% FTR and 90% OTD have to be achieved and all work products shall be stored in SVN
Benchmark target is (+/-) 10%
Internal review of all work products shall take place and be maintained in SVN
Review checklist shall be used for all Internal reviews
Weekly quality metrics shall be maintained and published
All communication in team or with manager will be maintained in SVN

## Slide 16: Assumptions
Module 1 :
We will be working on the local database(android preferences) inside mobile till web service is ready
It will be the static flow for basic demo purpose
Module 2 :
We will be working on the local database inside mobile till web service is ready
For iOS mobile application, we’ll be using the simulator for debugging, as we don’t have the apple developer membership (account) for profiles and certificates for testing in the real device
Module 3 :
For web service, we will be using local host and the local MySQL Database

## Slide 17: Risk Management
Risk Description | Probability of Occurrence | Impact | Mitigation Plan | Contingency Plan
Skill set mismatch(Project preferred skill set) | Low | High | Skill set mismatch will be raise to PM | Use one resource for R&D
If any Resource is absent due to emergency, it may hamper the deliverables | Medium | Medium | NA | Back up Resource will be used
Delay in response regarding issue | Medium | High | We will do follow-up and move to next task. | Work out an intermediate plan of what work can still progress
iOS developer account | Medium | High | We will test in simulator. | Try to apply it in later version.

## Slide 18: Change Management
Any functionality or activities that are not specifically mentioned in the scope are considered excluded from the scope of this proposal. If EasiCab so requires, such functionalities or activities can be considered as a change of scope and routed through EASi’s Change Management Process as illustrated.

## Slide 19: Change Management
Receive Change Request (CR)
Register CR in CR Log with CR Priority and Status: Open
Perform CR Impact Analysis
Estimate effort and cost
Estimate impact on schedule, if any
Check for additional specifications, if required
Communicate CR Impact to Customer
Estimate effort and cost
Estimate impact on schedule, if any
Request additional specifications, if required
Update Impacted activity and work products (including Specifications, if any)
Communicate to CR Stakeholders
Execute Change Request
Log the CR activity as a New Task
Update the necessary revision details / attributes for the impacted change and functionality
Update CR Log with CR Status: Closed
Update CR Log with CR Status: Dropped
Seek Approval from Customer CRequestor
Yes
Amend SOW / PO to Incorporate CR
No

## Slide 20: Project Deliverables
Working Code (UI/Functionalities)
.apk file of android
.ipa file of iOS
Manual test report
Note: All project reports, documents and source code will available in SVN Path:
https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/

## Slide 21: How to use

## Slide 22: Thank you
For more details, please contact:
EASi Embedded
Bangalore