## design_documents_review
Review Details :
Project Name |  |  | EASiCab | [9 empty] | Reviewer Name | Subhalaxmi
Review Date |  |  | 2016-08-04 | [9 empty] | Review Item Author/s | Design Documents
Phase of the Project |  |  | Phase 1 | [9 empty] | Project Phase Other Desc. | Phase 1 : Demo
Review Item |  |  | Design Documents | [9 empty] | Review Item Other Desc.
Reference Materials( SVN path ) |  |  | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/DesignDoc/EASiCABDesign_Doc.docx | [9 empty] | Type of Review | Senior Review
Review Log
Sl.No - Initials of module | Location of Defect/ Revision | Line #/ Section # | Description of Defect | Type of defect | Priority | Assigned to | Status | Review Team Recommendation | SVN revision of the Created issue no: | SVN revision of Modified issue | SVN revision of Fixed | Actual Implementation/ Revision | Verified By | Verification Date
1 | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/DesignDoc/EASiCABDesign_Doc.docx |  | Easi latest log with update svn link, Add header and footer |  | Low | Nitesh |  |  | 36 |  |  |  | Subhalaxmi | 2016-08-04
2 | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/DesignDoc/EASiCABDesign_Doc.docx |  | Architechture of application |  | High | Nitesh |  |  | 36 |  |  |  | Subhalaxmi | 2016-08-04
3 | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/DesignDoc/EASiCABDesign_Doc.docx |  | Database design not required. Add Svn link of database design to it. |  | Medium | Nitesh |  |  | 36 |  |  |  | Subhalaxmi | 2016-08-04
Total Defects |  | 0

## Guidelines
Guidelines to use the Review Log Sheet
1 | Please ensure to fill in the "Review Details" at start of the review. "Phase of Project" should not the current phase the project is under e.g. Design, Coding, Review ,Testing.
2 | In case of document reviews, "Location of Defect" refers to combination of page number / paragraph / line number.
3 | In case of code reviews, "Location of Defect" refers to combination of module name. The Line #/ Section # should be used to specify line number in application .
4 | For the Sl.No. of the defect, use intials of module to identify the module for which the defect is raised eg. Phase 1 or phase 2 of EASiCab
5 | A clear "Description of Defect" needs to be filled in and person responsible for addressing the issues is identified in the Assigned to column,
6 | The Status of error could be one of the following and to be set with consultation with the Moderator/ Reviewer.
|  | Open | Defect raised in the review
|  | Not a Defect | Analysis of defect indicated that it is not an Defect
|  | Fixed | Defect is fixed but pending verification from the Moderator/ Reviewer
|  | Verified | Defect has been verified to be fixed.
|  | Failed | Defect has failed Verification
7 | The Review Team Recommendation should be filled out in the Review Meeting and should be a description of the recommended change based on consensus or moderator direction.
8 | The Actual Implementation column should be filled in after the Assigned person has made changes to address the defect.
9 | The Verified By and Verification Date columns should be filled in after the items have been verified to be addressed.