## INTRODUCTION
ESTIMATION
TASK_STATUS
TIMELINE
TEAM STRUCTURE
REVIEW LOGS
METRICS
CAPA STATUS
MOM
RISK REGISTER
HARDWARE INVENTORY LIST
MILESTONES
STATUS MEETING
QUERY LIST
LESSONS LEARNT
ISSUES FOUND
FTR DEFINITION
DELIVERABLES
ESTIMATE SUMMARY
PED DOCUMENT
TRACEBALITY MATRIX
TEST PLAN
Note on B9: Author: Click on to open the respective file names.
EASi Cab

## TASK_STATUS
TASK STATUS
S.NO | FILE NAME | METHOD NAME | CYCLOMATIC COMPLEXITY | CODING START DATE | TASK COMPLETED DATE | ESTIMATED TIME CASE CREATION [HRS] | ACTUAL TIME [HRS] | AUTHOR | INTERNAL REWORK [HRS] | INTERNAL FTR | EXTERNAL REWORK [HRS] | EXTERNAL FTR | REVIEWER | ACTUAL 1st REVIEW HOURS | ESTIMATED 1st REVIEW HOURS | ESTIMATED 2nd REVIEW HOURS | ACTUAL 2nd REVIEW HOURS | REVIEWER STATUS | DELIVERED TO CUSTOMER
Note on E2: Author: Mention the start date when you create the test case.
Note on F2: Author: Mention the test case delivery date.
Note on H2: Author: Note the time taken for the test case creation.
Note on J2: Author: Mention the time taken for internal reworks reviewed by peer reviewer.
Note on K2: Author: This column is to mention the work product delivered is FTR[First time right].
Note on L2: Author: Mention the time taken for external reworks reviewed by customer.
Note on M2: Author: The External FTR is the work product[WP] has delivered to the customer and its been accepted. TEAM PERCEPTION -If you have delivered the WP to customer.Select this[Assuming delivered is correct]
Note on O2: Author: Actual time taken to Review
Note on P2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on Q2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on R2: Author: Review hours = Estimated time for test case creation *(1/3)
Note on S2: Author: Internal reviewer has to update the status regarding the reviewed WP.
Note on T2: Author: Delivered the particular work product to the customer.

## ESTIMATED_TIMElINE_PHASE1
ESTIMATED TIMELINE | [12 empty] | HOLIDAY |  |  |  | CREATION | [5 empty] | Resource Leave | [8 empty] | Resource:
[13 empty] | DEVELOPMENT |  |  |  | REVIEW | [5 empty] | Documentation | [8 empty] | 1 | Nitesh | 3 | Subhalaxmi
[13 empty] | COMPLETED |  |  |  | TESTING & REWORK | [14 empty] | 2 | Rohit | 4 | Nagarjun
TASK NAME | ESTIMATED Time for documentaion [HRS] | ESTIMATED Time for UI[HRS] | ESTIMATED Time for Functionalities[HRS] | ESTIMATED Time for integration of UI & Functionalities [HRS] | Task Owner | FIRST REVIEW/REWORKS HOURS | time axis 2016-07-29 to 2016-10-02
Internal Project Kick Off | bar: 2016-07-29
Final Project Kick Off
Design Document | 23 |  |  |  | NITESH | bar: 2016-08-01 to 2016-08-03; 2016-08-08 to 2016-08-09
Database document | 48 |  |  |  | ROHIT |  | 2016-08-01: 2; 2016-08-02: 2; 2016-08-03: 2; 2016-08-03: 2; 2016-08-05: 2; 2016-08-08: 2
Project tracker sheet & planning | 48 |  |  |  | SUBHALAXMI |  | 2016-08-01: 3; 2016-08-02: 3; 2016-08-03: 3; 2016-08-03: 3; 2016-08-09: 3; 2016-08-10: 3
UI/UX Flow | 48 |  |  |  | NAGARJUN | 16 | 2016-08-01: 4; 2016-08-02: 4; 2016-08-03: 4; 2016-08-03: 4; 2016-08-05: 4; 2016-08-08: 4
Reviews documents
Design Document |  |  |  |  | SUBHALAXMI | 8 | 2016-08-05: 3
Database document |  |  |  |  | NITESH | 8 | bar: 2016-08-11
UI/Functionalities
Splash.java & Login.java |  | 12 | 14 | 32 | NITESH/SUBHALAXMI |  | 2016-08-03: 1; 2016-08-05: 1; 2016-08-08: 3; 2016-08-12: 3; 2016-08-22: 3; 2016-08-23: 3; 2016-08-23: 1,3
Splash.java & Login review & rework |  |  |  |  | SUBHALAXMI | 8 | 2016-08-25: 3
Role.java |  | 12 | 12 | 8 | NITESH/SUBHALAXMI |  | 2016-08-08: 1; 2016-08-10: 1,3; 2016-08-11: 3; 2016-08-12: 1
Role.java review |  |  |  |  | SUBHALAXMI | 6 | 2016-08-16: 3
Registration.java |  | 24 | 32 | 16 | NITESH/SUBHALAXMI |  | 2016-08-16: 1; 2016-08-17: 1; 2016-08-18: 1,3; 2016-08-19: 3; 2016-08-22: 1; 2016-08-23: 1; 2016-08-25: 1; 2016-08-26: 3
Registration.java review & rework |  |  |  |  | SUBHALAXMI | 16 | 2016-08-29: 3; 2016-08-30: 1
Map.java |  | 16 | 32 | 24 | NITESH/SUBHALAXMI |  | 2016-08-17: 3; 2016-08-19: 1; 2016-08-26: 1; 2016-08-29: 1; 2016-08-30: 3; 2016-08-31: 1,3; 2016-09-01: 1,3
Map.java review & rework |  |  |  |  | SUBHALAXMI | 16 | 2016-09-01: 3; 2016-09-02: 1
NavigationDrawer |  | 20 | 12 | 8 | NITESH/SUBHALAXMI |  | 2016-09-06: 3; 2016-09-07: 3; 2016-09-08: 1,3; 2016-09-09: 3
NavigationDrawer review& rework |  |  |  |  | SUBHALAXMI | 8 | bar: 2016-09-09
TESTING | [6 empty] | 2016-09-12: 1,2,3; 2016-09-13: 1,2,3; 2016-09-13: 1,2,3
Server
Tools selection, installation, libraries and enviornmental setup |  |  | 16 |  | ROHIT |  | 2016-08-09: 2; 2016-08-10: 2
Tools selection, installation, libraries and enviornmental setup review |  |  |  |  | ROHIT | 8 | 2016-08-11: 2
Sample demo web API for hello world |  |  | 16 |  | ROHIT |  | 2016-08-12: 2; 2016-08-16: 2
Sample demo web API for hello world review and rework | [5 empty] | 8 | 2016-08-17: 2
Sample POST api performing back end logics |  |  | 24 |  | ROHIT |  | 2016-08-18: 2; 2016-08-19: 2; 2016-08-22: 2
Sample POST api performing back end logics review & rework |  |  |  |  | ROHIT/SUBHALAXMI | 20 | 2016-08-23: 2,3; 2016-08-23: 2,3
Sample GET api performing back end logics |  |  | 32 |  | ROHIT |  | 2016-08-25: 2; 2016-08-26: 2; 2016-08-29: 2; 2016-08-30: 2
Sample GET api performing back end logics review and rework |  |  |  |  | Rohit/Subhalaxmi/Nitesh | 24 | 2016-08-31: 2,1; 2016-09-01: 3
Sample PUT api performing back end operation |  |  | 32 |  | ROHIT |  | 2016-09-01: 2; 2016-09-02: 2; 2016-09-06: 2; 2016-09-07: 2
Sample PUT api performing back end operation review & rework | [5 empty] | 20 | 2016-09-08: 2,1; 2016-09-09: 2
Sample web api for database interaction |  |  | 32 |  | ROHIT |  | 2016-09-12: 2; 2016-09-13: 2; 2016-09-13: 2; 2016-09-15: 2
Sample web api for database interaction review & rework | [5 empty] | 16 | 2016-09-16: 2; 2016-09-19: 2
Sample api for implementing JDBC operation |  |  | 32 |  | ROHIT |  | 2016-09-20: 2; 2016-09-21: 2; 2016-09-22: 2; 2016-09-23: 2
Sample api for implementing JDBC operation review & rework | [5 empty] | 16 | 2016-09-26: 2; 2016-09-27: 2; 2016-09-28: 1,2,3; 2016-09-29: 1,2,3; 2016-09-30: 1,2,3
Note on G5: Author: 1st Review hours = Estimated time for test case creation *(1/3)
Note on H6: Author: Internal kick off meeting
Note on K8: NITESH
Note on L8: Nitesh
Note on M8: NITESH
Note on R8: NITESH REWORK ON DESIGN DOC AFTER REVIEWED
Note on S8: NITESH REWORK ON DESIGN DOC AFTER REVIEWED
Note on K9: Rohit
Note on L9: Rohit
Note on M9: Rohit
Note on N9: Rohit
Note on O9: Rohit
Note on R9: Rohit
Note on G10: Author: Its not defined as its an ongoing process. For improvement need to update it.
Note on K10: Subhalaxmi
Note on L10: Subhalaxmi
Note on M10: Subhalaxmi
Note on N10: Subhalaxmi
Note on S10: Subhalaxmi
Note on T10: Subhalaxmi
Note on K11: Nagarjun
Note on L11: Nagarjun
Note on M11: Nagarjun
Note on N11: Nagarjun
Note on O11: Nagarjun
Note on R11: Nagarjun
Note on O13: Subhalaxmi: Review design doc
Note on U14: NITESH Review database
Note on N16: NITESH UI
Note on O16: NITESH UI
Note on R16: SUBHALAXMI Android framework functionalities without webservices
Note on V16: SUBHALAXMI Android framework functionalities without webservices
Note on AF16: SUBHALAXMI integrating webservices
Note on AG16: SUBHALAXMI integrating webservices
Note on AH16: NITESH,SUBHALAXMI integrating webservices and testing
Note on BH16: TEAM
Note on BI16: TEAM
Note on BJ16: TEAM
Note on BK16: TEAM
Note on BL16: TEAM
Note on AI17: Subhalaxmi: Review
Note on R18: NITESH UI
Note on T18: NITESH,SUBHA UI & functionality
Note on U18: SUBHA functionality
Note on V18: NITESH UI & functionality SYNC
Note on BH18: TEAM
Note on BI18: TEAM
Note on BJ18: TEAM
Note on BK18: TEAM
Note on BL18: TEAM
Note on Z19: Subhalaxmi: Review
Note on BH19: TEAM
Note on BI19: TEAM
Note on BJ19: TEAM
Note on BK19: TEAM
Note on BL19: TEAM
Note on Z20: NITESH UI
Note on AA20: NITESH UI
Note on AB20: NITESH,SUBHA UI & functionality
Note on AC20: SUBHALAXMI : functionality without integrating webservices
Note on AF20: NITESH functionality
Note on AG20: NITESH functionality
Note on AI20: NITESH webservice integration
Note on AJ20: SUBHA webservice integration
Note on BH20: TEAM
Note on BI20: TEAM
Note on BJ20: TEAM
Note on BK20: TEAM
Note on BL20: TEAM
Note on AM21: Subhalaxmi: Review
Note on AN21: NITESH Review
Note on BH21: TEAM
Note on BI21: TEAM
Note on BJ21: TEAM
Note on BK21: TEAM
Note on BL21: TEAM
Note on AA22: SUBHALAXMI : ui
Note on AC22: NITESH UI
Note on AJ22: NITESH functionality
Note on AM22: NITESH functionality
Note on AN22: SUBHALAXMI : ui
Note on AO22: NITESH,SUBHALAXMI functionality
Note on AP22: NITESH,SUBHALAXMI functionality
Note on BH22: TEAM
Note on BI22: TEAM
Note on BJ22: TEAM
Note on BK22: TEAM
Note on BL22: TEAM
Note on AP23: Subhalaxmi: Review
Note on AQ23: NITESH Review
Note on BH23: TEAM
Note on BI23: TEAM
Note on BJ23: TEAM
Note on BK23: TEAM
Note on BL23: TEAM
Note on AU24: SUBHALAXMI : ui
Note on AV24: SUBHALAXMI : ui
Note on AW24: Nitesh,SUBHALAXMI : ui & functionality
Note on AX24: SUBHALAXMI functionality
Note on BH24: TEAM
Note on BI24: TEAM
Note on BJ24: TEAM
Note on BK24: TEAM
Note on BL24: TEAM
Note on AX25: NITESH Review
Note on BH25: TEAM
Note on BI25: TEAM
Note on BJ25: TEAM
Note on BK25: TEAM
Note on BL25: TEAM
Note on BA26: TEAM
Note on BB26: TEAM
Note on BC26: TEAM
Note on BD26: Author: Will complete and submitt demo
Note on S28: Rohit
Note on T28: Rohit
Note on U29: Rohit: Review, testing and rework to complete
Note on V30: Rohit
Note on Z30: Rohit
Note on AA31: Rohit: Review, testing and rework to complete
Note on AB32: Rohit
Note on AC32: Rohit
Note on AF32: Rohit
Note on AG33: Rohit,SUBHALAXMI review,test and rework (if any)
Note on AH33: Rohit,SUBHALAXMI review,test and rework (if any)
Note on AI34: Rohit
Note on AJ34: Rohit
Note on AM34: Rohit
Note on AN34: Rohit
Note on AO35: Rohit,NITESH review,test and rework (if any)
Note on AP35: SUBHALAXMI review,test and rework (if any)
Note on AP36: Rohit
Note on AQ36: Rohit
Note on AU36: Rohit
Note on AV36: Rohit
Note on AW37: Rohit,NITESH review,test and rework (if any)
Note on AX37: Rohit: Review, testing and rework to complete
Note on BA38: Rohit
Note on BB38: Rohit
Note on BC38: Rohit
Note on BD38: Rohit
Note on BE39: Rohit: Review, testing and rework to complete
Note on BH39: Rohit: Review, testing and rework to complete
Note on BI40: Rohit
Note on BJ40: Rohit
Note on BK40: Rohit
Note on BL40: Rohit
Note on BO41: Rohit: Review, testing and rework to complete
Note on BP41: Rohit: Review, testing and rework to complete
Note on BQ41: TEAM
Note on BR41: TEAM
Note on BS41: TEAM

## ACTUAL_TIMELINE_PHASE1
ACTUAL TIMELINE | [12 empty] | Holiday |  |  |  | Creation | [5 empty] | Resource Leave | [8 empty] | Resource:
[13 empty] | Development |  |  |  | Review | [5 empty] | Documentation | [8 empty] | 1 | Nitesh | 3 | Subhalaxmi
[13 empty] | Completed |  |  |  | Testing & rework | [5 empty] | Survey | [8 empty] | 2 | Rohit | 4 | Nagarjun
TASK NAME | ESTIMATED Time for documentaion [HRS] | ESTIMATED Time for UI[HRS] | ESTIMATED Time for Functionalities[HRS] | ESTIMATED Time for integration of UI & Functionalities [HRS] | FIRST REVIEW/REWORKS HOURS | Actual Time taken( task+rework+review) HOURS | 2016-07-29 | 2016-07-30 | 2016-07-31 | 2016-08-01 | 2016-08-02 | 2016-08-03 | 2016-08-04 | 2016-08-05 | 2016-08-06 | 2016-08-07 | 2016-08-08 | 2016-08-09 | 2016-08-10 | 2016-08-11 | 2016-08-12 | 2016-08-13 | 2016-08-14 | 2016-08-15 | 2016-08-16 | 2016-08-17 | 2016-08-18 | 2016-08-19 | 2016-08-20 | 2016-08-21 | 2016-08-22 | 2016-08-23 | 2016-08-24 | 2016-08-25 | 2016-08-26 | 2016-08-27 | 2016-08-28 | 2016-08-29 | 2016-08-30 | 2016-08-31 | 2016-09-01 | 2016-09-02 | 2016-09-03 | 2016-09-04 | 2016-09-05 | 2016-09-06 | 2016-09-07 | 2016-09-08 | 2016-09-09 | 2016-09-10 | 2016-09-11 | 2016-09-12 | 2016-09-13 | 2016-09-14 | 2016-09-15 | 2016-09-16 | 2016-09-17 | 2016-09-18 | 2016-09-19 | 2016-09-20 | 2016-09-21 | 2016-09-22 | 2016-09-23 | 2016-09-24 | 2016-09-25 | 2016-09-26 | 2016-09-27 | 2016-09-28 | 2016-09-29 | 2016-09-30 | 2016-10-01 | 2016-10-02 | 2016-10-03 | 2016-10-04 | 2016-10-05 | 2016-10-06 | 2016-10-07 | 2016-10-08 | 2016-10-09 | 2016-10-10 | 2016-10-11 | 2016-10-12 | 2016-10-13 | 2016-10-14 | 2016-10-05 | 2016-10-16
Internal Project Kick Off
Final Project Kick Off
Design Document | 23 |  |  |  |  | 40 |  |  |  | 1 | 1 | 1 |  |  |  |  | 1 | 1
Design Document Review |  |  |  |  | 8 | [8 empty] | 3
Database document | 48 |  |  |  |  | 32 |  |  |  | 2 | 2 | 2 | 2
Database document review |  |  |  |  | 8 | [14 empty] | 1 | [6 empty] | 2 | 2
Project tracker sheet & planning | 48 |  |  |  |  | 42 |  |  |  | 3 | 3 | 3 | 3 |  |  |  |  | 3 | 3
UI/UX Flow | 48 | [8 empty] | 4 | 4 | 4 | 4 | 4
UI/Functionalities
Splash.java & Login.java |  | 12 | 14 | 32 | [8 empty] | 1 | 1 |  |  | 3 |  |  |  | 3 | [40 empty] | 3 | 3 |  |  | 1,3
Splash.java & Login review & rework |  |  |  |  | 8 | [61 empty] | 3
Role.java |  | 12 | 12 | 8 | [12 empty] | 1 |  | 1,3 | 3 | 1
Role.java review |  |  |  |  | 6 | [19 empty] | 3
Registration.java |  | 24 | 32 | 16 | [20 empty] | 1 | 1 | [35 empty] | 1 | 1 |  |  |  | 1 | 3
Registration.java review & rework |  |  |  |  | 16 | [63 empty] | 3 | 1
Map.java |  | 16 | 32 | 24 | [21 empty] | 3 |  | 1 | [37 empty] | 1 |  |  | 1 | 3 |  |  | 1,3 | 1,3
Map.java review & rework |  |  |  |  | 16 | [64 empty] | 3 |  |  |  |  | 3 | 1
NavigationDrawer |  | 20 | 12 | 8 | [72 empty] | 3 |  |  | 3 |  | 1,3 | 3
NavigationDrawer review& rework |  |  |  |  | 8 | [77 empty] | 1
TESTING | [51 empty] | 1,2,3 | 1,2,3 | 1,2,3
Survey & KT
Meetings with stakeholders | [33 empty] | 1,2,3
Collecting information | [33 empty] | 1,2,3
Preparing required docs & records | [27 empty] | 3 |  |  | 3 | 3 | 1,2,3 |  | 2,3
Preparing questions, Survey Monkey Forms
Server
Tools selection, installation, libraries and enviornmental setup |  |  | 16 | [10 empty] | 2 |  |  | 2 | [13 empty] | 1 | 1 | 1 | 1 | 1 |  |  | 3 | 3
Tools selection, installation, libraries and enviornmental setup review |  |  |  |  | 8 | [12 empty] | 2
Sample demo web API for hello world |  |  | 16 | [15 empty] | 2 | 2
Sample demo web API for hello world review and rework |  |  |  |  | 8 | [15 empty] | 2
Sample POST api performing back end logics |  |  | 24 | [21 empty] | 2 | 2 |  |  |  |  | 2
Sample POST api performing back end logics review & rework |  |  |  |  | 20 | [41 empty] | 2,3 | 2,3
Sample GET api performing back end logics |  |  | 32 | [30 empty] | 2 | 2 |  |  | 2 | 2
Sample GET api performing back end logics review and rework |  |  |  |  | 24 | [34 empty] | 2
Sample PUT api performing back end operation |  |  | 32 | [37 empty] | 2 | 2 |  |  |  | 2 | 2
Sample PUT api performing back end operation review & rework |  |  |  |  | 20 | [42 empty] | 2,1 | 2
Sample web api for database interaction |  |  | 32 | [48 empty] | 2 | 2 | 2 | 2
Sample web api for database interaction review & rework |  |  |  |  | 16 | [50 empty] | 2 |  |  | 2
Sample api for implementing JDBC operation |  |  | 32 | [56 empty] | 2 | 2 | 2 | 2
Sample api for implementing JDBC operation review & rework |  |  |  |  | 16 | [60 empty] | 2 | 2 | 1,2,3 | 1,2,3 | 1,2,3
Note on BE3: Author: Planning to complete our Survey
Note on H6: Author: Internal kick off meeting
Note on AB7: Author: Formal kick off meeting
Note on K8: NITESH
Note on L8: Nitesh
Note on M8: NITESH not reviewd
Note on R8: NITESH REWORK ON DESIGN DOC AFTER REVIEWED
Note on S8: NITESH REWORK ON DESIGN DOC AFTER REVIEWED
Note on O9: Subhalaxmi: Review design doc: updated review in log
Note on G10: Author:
Note on K10: Rohit
Note on L10: Rohit
Note on M10: Rohit
Note on N10: Rohit: completed not reviewed. Moved to task number 28
Note on U11: NITESH Review database
Note on AB11: Rohit REWORK ON Database Doc
Note on AC11: Rohit REWORK ON Database Doc
Note on F12: Author: Its not defined as its an ongoing process. For improvement need to update it.
Note on G12: Author: For improvement need to update it.
Note on K12: Subhalaxmi
Note on L12: Subhalaxmi
Note on M12: Subhalaxmi
Note on N12: Subhalaxmi
Note on S12: Subhalaxmi
Note on T12: Subhalaxmi updated monitor tracker sheet
Note on F13: Author: Its not defined as its an ongoing process. For improvement need to update it.
Note on K13: Nagarjun
Note on L13: Nagarjun
Note on M13: Nagarjun
Note on N13: Nagarjun
Note on O13: Nagarjun completed login,registration,home,profilev etc- screens required for demo flow
Note on N15: NITESH UI
Note on O15: NITESH UI
Note on R15: SUBHALAXMI Android framework functionalities without webservices
Note on V15: SUBHALAXMI is on Leave Android framework functionalities without webservices
Note on BL15: SUBHALAXMI integrating webservices
Note on BM15: SUBHALAXMI integrating webservices
Note on BP15: NITESH,SUBHALAXMI integrating webservices and testing
Note on BQ16: Subhalaxmi: Review
Note on R17: NITESH started UI
Note on T17: NITESH,SUBHA UI & functionality
Note on U17: SUBHA functionality
Note on V17: NITESH UI & functionality SYNC
Note on Z18: Subhalaxmi: Review
Note on Z19: NITESH UI
Note on AA19: NITESH UI
Note on BL19: NITESH functionality
Note on BM19: NITESH functionality
Note on BQ19: NITESH webservice integration
Note on BR19: SUBHA webservice integration
Note on BS20: Subhalaxmi: Review
Note on BT20: NITESH Review
Note on AA21: SUBHALAXMI : ui
Note on AC21: NITESH UI
Note on BP21: NITESH functionality
Note on BS21: NITESH functionality
Note on BT21: SUBHALAXMI : ui
Note on BW21: NITESH,SUBHALAXMI functionality
Note on BX21: NITESH,SUBHALAXMI functionality
Note on BT22: Subhalaxmi: Review
Note on BY22: Subhalaxmi: Review
Note on BZ22: NITESH Review
Note on CA23: SUBHALAXMI : ui
Note on CD23: SUBHALAXMI : ui
Note on CF23: Nitesh,SUBHALAXMI : ui & functionality
Note on CG23: SUBHALAXMI functionality
Note on CG24: NITESH Review
Note on BB25: TEAM
Note on BC25: TEAM
Note on BD25: TEAM
Note on BE25: Author: Will complete and submitt demo
Note on AJ27: Team: meeting and planning
Note on AJ28: Team: meeting and planning
Note on AC29: Created reports and sheets to track each stage of planning
Note on AG29: Created reports and sheets to track each stage of planning
Note on AH29: Created reports and sheets to track each stage of planning
Note on AI29: Prepared POC PPT
Note on AK29: Rohit & Subhalaxmi Prepare survey reports after meeting with Ge Lighting team
Note on O32: Rohit
Note on R32: Rohit
Note on AG32: Nitesh
Note on AH32: Nitesh:
Note on AI32: Nitesh:
Note on AJ32: Nitesh: Installed in Lab Laptop
Note on AK32: Nitesh: Installed in Lab Laptop
Note on AN32: Subhalaxmi
Note on AO32: Subhalaxmi
Note on S33: Rohit: Review, testing and rework to complete
Note on T34: Rohit
Note on U34: Rohit
Note on V35: Rohit: Review, testing and rework to complete
Note on Z36: Rohit 4 hours, Rest did R&D on OBD poc.
Note on AA36: Rohit 5 hours, Rest did R&D on OBD poc.
Note on AG36: Rohit
Note on AW37: Rohit,SUBHALAXMI Demo: review,test and rework (if any)
Note on AX37: Rohit,SUBHALAXMI review,test and rework (if any)
Note on AJ38: Rohit
Note on AK38: Rohit
Note on AN38: Rohit
Note on AO38: Rohit
Note on AP39: Rohit on Leave
Note on AQ40: Rohit on Leave
Note on AR40: Rohit on Leave
Note on AV40: Rohit
Note on AW40: Rohit
Note on AX41: Rohit,NITESH review,test and rework (if any)
Note on AY41: Rohit: Review, testing and rework to complete
Note on BB42: Rohit
Note on BC42: Rohit
Note on BD42: Rohit
Note on BE42: Rohit
Note on BF43: Rohit: Review, testing and rework to complete
Note on BI43: Rohit: Review, testing and rework to complete
Note on BJ44: Rohit
Note on BK44: Rohit
Note on BL44: Rohit
Note on BM44: Rohit
Note on BP45: Rohit: Review, testing and rework to complete
Note on BQ45: Rohit: Review, testing and rework to complete
Note on BR45: TEAM
Note on BS45: TEAM
Note on BT45: TEAM

## TEAM_STRUCTURE
EmployeeCode | EmployeeName | 1-August-2016 to 07-August-2016 | 8-August-2016 to14-August-2016 | 15-August-2016 to 21-August-2016 | 22-August-2016 to 28-August-2016 | 29-August-2016 to 04-Sept-2016 | 05-September-2016 to 11-Sept-2016 | 12-September-2016 to 18-Sept-2016 | 19-September-2016 to 25-Sept-2016
|  | Week 31 | Week 32 | Week 33 | Week 34 | Week 35 | Week 36 | Week 37 | Week 38
4463 | Nitesh Kumar | Week 31: 40; Week 32: 16
5030 | Rohit Soraf | Week 31: 40; Week 32: 16
4335 | Subhalaxmi | Week 31: 40; Week 32: 16
Billable hours |  | Week 31: HRS; Week 33: Billable
Engineer 1 | Nitesh | Week 31: 56; Week 33: Buffer
Engineer 2 | Rohit Soraf | Week 31: 56
Engineer 3 | Subhalaxmi | Week 31: 56
Engineer 4
Total Engineer week hours |  | Week 31: #NAME?
TOTAL EFFORT | Hours
3 Engineer | 168
Note on C6: Green colour indicates resource worked on weekends.

## REVIEW_LOGS
REVIEWS LOG
S.NO | REVIEW LOG
1 | Database Document
2 | Design Document
3 | SplashScreen.java
4 | LoginScreen.java
Note on B5: Author: For review logs click on respective file name.

## METRICS
METRICS & TIME SHEET TRACKER
S.NO | TIME SHEET WEEK NO | METRICS WEEK NO
1
2
3
4
5
6
7
8
Note on B5: Author: click on time sheet column for respective time sheet week.
Note on C5: Author: click on Metrics week no column for respective metrics week.

## CAPA
CAPA TRACKER
S.NO | CAPA WEEK
1 | CAPA WEEK NO
Note on B4: Author: Mention which week CAPA has been raised.Click on the link to open the document.
Note on B5: Author: This is CAPA template

## MOM
MOM TRACKER
S.NO | DATE | MEETING
1 | 2016-07-29 | Internal_Kickoff_Meeting
2
Note on C5: Author: Click on the respective meeting for MOM.

## FTR_DEFINITION
FTR DEFINITIONS OF Phase 1 EASiCab
Per 100 LOC or Per 100 Test Cases
FTR %age | 100 | 95 | 90 | 80 | 75 | 0
Critical | 0 | 0 | 0 | 0 | 0 | 1
Major | 0 | 0 | 0 | 1 | upto 5 | >6
Medium | 1 | 5 | 5 to 10 | 10 to 15 | 15 to 25 | >26
Minor | upto 5 | 5 to 15 | 15 to 25 | 25 to 35 | 35 to 50 | >51
Category | Description
Critical | [1].Application is not secuired.
[2]. On installation of the app, it will Crash, Hang or affect the device full operating system. It may need to re-flashing the OS.
[3].Viruse found and affect other devices.
Major | [1].If application is crashing without any notification i.e. ANR
[2].Unexpected application behaviour. i.e. Opening page not as per expected.
[3]. No error handling, No required notification, No network handling or notification for user
[4]. Data mismatch. i.e. Details are not coming as per login user.
Medium | [1].No vallidation for entry fields i.e email, password or empty entries.
[2]. Not supporting all screen sizes. Positioning of views is not constant.
[3].Unexpected application behaviour in perticular devices.
Minor | [1] UI component sizes mis-match
[2].Text color/size/font mismatch. Text of views mismatch.
Note on B12: Author:
Note on B14: Author: On installation, it may affect full operating system.
Note on B18: Author:
Note on B20: Author: On clicking of submit button in login page leads to register page instead of home page
Note on B22: Author:
Note on B24: Author: The details displayed is not as per the login user. On success full login, the details are available are of other user (not loginuser). Expected result not available as per valid user.
Note on B26: Author:
Note on B28: Author:
Note on B30: Author: Same piece of code not working in few devices(any) or showing ANR in perticular device/version. It may be secuirity permission issues or device theme issues
Note on B32: Author: Icon size mismatch from recuired documents
Note on B34: Author: Textv color, text size , text string are differing.Spelling mistake, positioning or spacing between text etc.

## DELIVERABLES
DELIVERABLES
SOURCE CODE
MANUAL GUIDE
.apk files
.ipa files

## ESTIMATE_SUMMARY
ACTUAL VS ESTIMATED SUMMARY
Version 1
ESTIMATED TIME |  | ACTUAL TIME |  | TOTAL ESTIMATED TIME V1 |  | TOTAL ESTIMATED TIME V2
[5 empty] | Hours |  | Hours
UI ESTIMATED | HOURS | UI ACTUAL | HOURS | UI Development |  | UI Development
Estimated UI development (hrs) |  | Actual UI development (hrs) |  | Functionality Development |  | Functionality Development
Estimated UI development testing(multiple screen) before submitting to review (hrs) |  | Actual UI development testing(multiple screen) before submitting to review (hrs) |  | Integration of UI andFunctionality Development |  | Integration of UI andFunctionality Development
Estimated 1st review (hrs) |  | Actual 1st review (hrs) |  | Total | 0 | Total
Estimated 2nd review (hrs) |  | Actual 2nd review (hrs)
Internal rework (hrs) |  | Internal rework (hrs)
External rework (hrs) |  | External rework (hrs) |  | TOTAL ACTUAL TIME
Estimated time for report preparation |  | Actual time for report preparation |  |  | Hours
Estimated total |  | Actual total |  | UI Development
UI Development
Integration of UI andFunctionality Development
FUNCTIONALITIES ESTIMATED | HOURS | FUNCTIONALITIES ACTUAL | HOURS | Total | 0
Estimated for functionalities development (hrs) |  | Actual time for functionalities development (hrs)
Estimated time for integrating functionalities and UI development (hrs) |  | Actual time for integrating functionalities and UI development (hrs)
Estimated time for internal testing before submitting to review (hrs) |  | Actual time for internal testing before submitting to review (hrs)
Estimated review hours |  | Actual review hours
Estimated time for Report preparation |  | Actual time for Report preparation
External rework
ESTIMATED TOTAL |  | ACTUAL TOTAL
Webservices ESTIMATED | HOURS | Webservices ACTUAL | HOURS
Estimated for webservices supporting tools and languages & enviornment setups |  | Actual for webservices supporting tools and languages & enviornment setups
Estimated for Webservice learning and creation (samples) |  | Actual time for Webservice learning and creation (samples)
Estimated time for application based apis development (hrs) |  | Actual time for application based apis development (hrs)
Estimated time for internal testing before submitting to review/integration(hrs) |  | Actual time for internal testing before submitting to review/integration (hrs)
Estimated review/internal rework hours |  | Actual review/internal reworks hours
Estimated time for Report preparation |  | Actual time for Report preparation
External rework
ESTIMATED TOTAL |  | ACTUAL TOTAL
Note on M5: Author: This Estimate was sent to customer for V4.19
Note on Q5: Author: This Estimate for V4.22.
Note on B8: Author: Estimated time for v4.19 1st sent to customer = 437hrs Changed estimate V4.22 = 440.75 hrs
Note on B9: Author: Estimated time for v4.19 1st sent to customer = 457hrs Changed estimate V4.22 = 437hrs
Note on T9: Author: Two layers of review added in new estimate
Note on B14: Author: Estimated time for v4.19 1st sent to customer = 91.4hrs Changed estimate V4.22 = 87.4hrs
Note on B15: Author: Total Estimated time for UTC v4.19 1st sent to customer excluding the 1st and 2nd review hours = 985.95hrs Changed estimate V4.22 including 1st and 2nd review hours =1093.13 hrs