## Sheet1
Project: | Easicab
Manager: | Deepa Shastry
SVN: | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/Manage
Task description | 3 point Estimate(Hours) |  |  | Assigned to | Start date | Remaining effort(hours) | Actual Effort(Hours) | End date | Current Status | Comments | Review - assigned to | Review - Start date | Review - Remaining effort | Review - End date | Approved?
| Best | Average | Worst |  |  | Average
Module 1- DEMO FLOW of Application
Deign Documents | 16 | 24 | 32 | Nitesh | 2016-07-25 | 6 | 18 | 2016-07-27 | Open | Not reviewed | Rohit | 2016-08-03
Database Design Modules Documents | 32 | 40 | 45 | Rohit | 2016-07-18 | 6 | 34 | 2016-07-22 | Open | Not reviewed | Subhalaxmi | 2016-08-03
Web service - (R & D) and Installation & enviornmental set up, Simple Hello world application | 40 | 48 | 64 | Rohit | 2016-07-25 | 8 | 40 | 2016-08-01 | Closed | Tools confirmed to be used - Eclipse, Apache Tomcat as local server, MySQL database for data storage Tools have been installed The environment set up like the path set up, libraries installations and tools integration has been done Sample Hello world application created and executed for initial understanding Created Maven project for the same Hello world application, but the moved back to the non maven approach due to dependencies error
UI/UX flow | 40 | 48 | 64 | Nagarjun | 2016-07-20 | 0 | 48 | 2016-07-27 | Open
Application Flow- Splash Screen, LogIn,Registration,Role Page UI | 48 | 56 | 64 | Subhalaxmi | 2016-07-21 | 0 | 56 | 2016-07-29 | Open | Now we can impliment the UI/UX design
Map integration | 32 | 40 | 52 | Sharath | 2016-07-21 | 0 | 45 | 2016-07-27 | Not completed
Review of design document | 8 | 10 | 16 | Subhalaxmi | 2016-08-03 |  |  |  | Not Started
Review of database document | 8 | 8 | 16 | Nitesh | 2016-08-03 |  |  |  | Not Started
Web Service - Sample GET & POST application performing some operation from the back-end | 40 | 48 | 56 | Rohit | 2016-08-01 |  |  |  | In Progress
Implement UI as per the UI flow (Splash Screen & Login) | 8 | 10 | 16 | Nitesh | 2016-08-01 |  |  |  | In Progress
Implimenting design as per UI/UX flow
TOTAL | 224 | 274 | 353

## Sheet2
Date | Remaining work effort | Remaining review effort | Total remaining effort (hours) | Comments
0
2015-05-22 | 6885 |  | 6885
2015-05-29 | 6844.5 |  | 6844.5
2015-06-05 | 6790.5 |  | 6790.5
2015-06-12 | 6718.5 |  | 6718.5
2015-06-19 | 6691.5 |  | 6691.5
2015-06-26 | 6646.5 |  | 6646.5
2015-07-03 | 6592.5 |  | 6592.5
2015-07-10 | 6547.5 |  | 6547.5