## Version History (hidden)
Name of the document: |  | Project Metrics Dashboard
Document Number: |  | -
Version No: |  | 1
Prepared by: |  | Dinesh Pandiyan
Reviewed by:
Approved by:
Version History
S No | Change Description | Version No. | prepared by | approved by | Remarks
1 | Project metrics Dashboard template Created | 1 | Dinesh Pandiyan | Tamilselvan

## Project Metrics - Definition
Metric Definition
Project metrics | Target | Formula to Calculate
First Time Right (FTR - Customer) | 95% | Total # of projects delivered first time right without any defects in a given month / Total # of projects delivered in a given month
First Time Right (FTR - Internal) | 95% | Total # of projects delivered first time right without any defects in a given month / Total # of projects delivered in a given month
Schedule Adherence (SA) | 90% | Total # of projects delivered (Final delivery) within initially agreed time in a given month / Total # of projects delivered in a given month
Benchmark Performance (BP) | ±10% | (Total estimated effort - Total Actual Effort) for all projects in a given month / Total estimated effort for all projects in a given month
Customer Satisfaction Index | < 2.0 | Average of all customer satisfaction rating in a given quarter on a 1 - 4 scale
Utilization Factor | 80% | Total actual billed hours for all projects in a given month / Total available hours in a given month
Average Team Training Hour | 4% | Total training hours spent by the team in a given month / Total available hours in a given month
NOTE:
1. Total # Projects is in the view of customer, differentiate between task and project (work packets for CNH, program for CAE Design, project for Chrysler, SOW for safran, tasks for EASi LLC etc.,)
2. Available hours is defined as number of days an employee is assigned to a particular team * no of hours per day (8 hrs or 9 hrs). Manpower report will be the master for assignment information. For ex. For a 20 working day month @ 8 hrs per day, available hours per employee will be 160 hrs
3. For schedule adherence, the final delivery date after all reworks will be considered as performance. On-time is the date and time as agreed to initially, any extensions sought and agreed due to change in scope will be considered. Extensions granted by customer to overcome our constraints (network issue, resource non-availability etc.,) will be considered as revised delivery date.
4. BP is +ve when actual hours is more than estimated, -ve when actual hours is lower than estimated
5. CSAT scores are as follows: 1-Very Satisfied, 2-Satisfied, 3-Dissatisfied, 4-Very Dissatisfied. Frequency will be Quarterly for In-House projects and Half-yearly for CSS engagements. Refer to the new survey template from NA.
6. If the project metrics are out of control, Corrective actions must be taken.
7. Prpject Health Indicator criteria:
RED ( R ) - Below 75 % of Completion YELLOW ( Y ) - 75 % to 90 % of completion GREEN ( G ) - Above 90 % of completion
7. Any Queries, Please contact mjunaidi@easi.com /arukrish@easi.com

## Project metrics generator
Project / Project Team: |  | CNHi - APP | Prepared By: |  |  | Deepa Shastry
Customer Name |  | CNHi | Reviewed & Approved By:
Project Manager: |  |  | Submitted on: |  |  | 2016-01-13
Project metrics generator
S No | Metrics |  | Wk53 | WK01
1 | First Time Right- (FTR - Customer-Modules | Total # of modules delivered first time right | 10 | 0
|  | Total # of modules delivered | 10 | 0
|  | Actual | 100% | #DIV/0!
|  | Target | 95% | 95% | 95% | 95% | 95% | 95%
2 | First Time Right- (FTR - Customer-Modules) | Total # of modules delivered First Time Right | 6 | 0
|  | Total # of modules delivered | 10 | 0
|  | Actual | 60% | #DIV/0!
|  | Target | 95% | 95% | 95% | 95% | 95% | 95%
3 | First Time Right (FTR - Internal) | Total # of modules' delivered First Time Right | 6 | 0
|  | Total # of modules' delivered | 10 | 0
|  | Actual | 60% | #DIV/0!
|  | Target | 95% | 95% | 95% | 95% | 95% | 95%
4 | Schedule Adherence- (SA-Modules) | Total # of UI modules completed on time | 10 | 0
|  | Total # of UI modules completed | 10 | 0
|  | Actual | 100% | #DIV/0! |  |  | 6%
|  | Target | 90% | 90% | 90% | 90% | 90% | 90%
5 | Schedule Adherence- (SA-WP) | Total # of modules delivered to customer on time | 10 | 0
|  | Total # of modules delivered | 10 | 0
|  | Actual | 100% | #DIV/0!
|  | Target | 90% | 90% | 90% | 90% | 90% | 90%
6 | Benchmark Performance (BP) | Total estimated effort on the tasks/modules | 468 | 0
|  | Actual effort spent on the tasks/modules | 468 | 0
|  | Actual | 0% | #DIV/0!
|  | Target | 10% | 10% | 10% | 10% | 10% | 10%
7 | Customer Satisfaction Index | Actual
|  | Target | 2 | 2 | 2 | 2 | 2 | 2
8 | Utilization Factor | Total Billed hours for all delivered | 135
|  | Total available hours | 180
|  | Actual | 75%
|  | Target | 80% | 80% | 80% | 80% | 80% | 80%
9 | Rework Hours | Internal Rework hours | 0
|  | External Rework hours | 0 | 0
10 | Leave Factor | Total Vacation/leave hours during the week | 0
|  | Total available hours | 180
10 | Average Team Training Hour | Total training hours spent by the team | 0
|  | Total available hours | 180
|  | Actual | 0%
|  | Target | 4% | 4% | 4% | 4% | 4% | 4%
NOTE:
1. Update Particulars in "WHITE" cells. Project metrics will be automatically calculated.

## Trend Chart
PROJECT METRICS DASHBOARD
Other Trend charts (If any - optional)
NOTE:
1. 'Chart data range' has to be updated on monthly basis.

## List of Projects Completed
List of Completed projects
S No | Project Name | Project ID | Project Schedule |  |  |  |  | Project efforts |  | FTR (Customer) Y (Yes) / N (No) | Remarks
|  |  | Planned Start Date | Committed Delivery Date | Actual Start Date | Actual Delivery Date | Delivered On Time? Y (Yes) / N (No) | Total Estimated effort | Actual Effort being spent
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124

## List of Inprogress Projects-RYG
List of Inprogress projects
S No | Project Name | Project ID | Project Health Indicator (R-Red Y-Yellow G-Green) | Project Schedule |  |  |  | Project efforts |  | Remarks
|  |  |  | Planned Start Date | Committed Delivery Date | Actual Start Date | Actual Delivery Date | Total Estimated effort | Actual Effort being spent
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115

## Sheet1
8 | 2 | 0.2 | 0.3 | 10.5 | 10.5 | 0.76 | 11.26 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 3 | 0.875 | 0.2 | 0.5 | 0.35 | 4.925
2.5 | 1 | 0.2 | 0.3 | 4 | 4 | 0.76 | 4.76 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.75 | 0.25 | 0.2 | 0.5 | 0.35 | 2.05
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
6 | 3 | 0.2 | 0.3 | 9.5 | 9.5 | 0.76 | 10.26 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.75 | 0.25 | 0.2 | 0.5 | 0.35 | 2.05
5.5 | 1 | 0.2 | 0.3 | 7 | 7 | 0.76 | 7.76 | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
0.8 | 0.25 | 0.2 | 0.3 | 1.55 | 1.55 | 0.76 | 2.31 | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
0.8 | 0.25 | 0.2 | 0.3 | 1.55 | 1.55 | 0.76 | 2.31 | 8 | 2 | 0.2 | 0.3 | 10.5 | 8 | 2 | 0.2 | 0.5 | 10.7 | 6 | 2 | 0.2 | 0.5 | 0.35 | 9.05
8 | 2 | 0.2 | 0.3 | 10.5 | 10.5 | 0.76 | 11.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
5 | 1 | 0.2 | 0.3 | 6.5 | 6.5 | 0.76 | 7.26 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
0.8 | 0.25 | 0.2 | 0.3 | 1.55 | 1.55 | 0.76 | 2.31 | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
0.8 | 0.25 | 0.2 | 0.3 | 1.55 | 1.55 | 0.76 | 2.31 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 2 | 1 | 0.2 | 0.5 | 0.35 | 4.05
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 5 | 1.25 | 0.2 | 0.3 | 6.75 | 5 | 1.25 | 0.2 | 0.5 | 6.95 | 3 | 1.25 | 0.2 | 0.5 | 0.35 | 5.3
3 | 1 | 0.2 | 0.3 | 4.5 | 4.5 | 0.76 | 5.26 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
1.3 | 0.5 | 0.2 | 0.3 | 2.3 | 2.3 | 0.76 | 3.06 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
7 | 2 | 0.2 | 0.3 | 9.5 | 9.5 | 0.76 | 10.26 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 1.5 | 0.75 | 0.2 | 0.5 | 0.35 | 3.3
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 6 | 1.5 | 0.2 | 0.3 | 8 | 6 | 1.5 | 0.2 | 0.5 | 8.2 | 3 | 1.5 | 0.2 | 0.5 | 0.35 | 5.55
3 | 0.5 | 0.2 | 0.3 | 4 | 4 | 0.76 | 4.76 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 1 | 1 | 0.2 | 0.5 | 0.35 | 3.05
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
2 | 0.5 | 0.2 | 0.3 | 3 | 3 | 0.76 | 3.76 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 3 | 0.875 | 0.2 | 0.5 | 0.35 | 4.925
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.25 | 0.5 | 0.2 | 0.5 | 0.35 | 2.8
1 | 0.5 | 0.2 | 0.3 | 2 | 2 | 0.76 | 2.76 | 0.75 | 0.1875 | 0.2 | 0.3 | 1.4375 | 0.75 | 0.1875 | 0.2 | 0.5 | 1.6375 | 0.5 | 0.1875 | 0.2 | 0.5 | 0.35 | 1.7375
2 | 0.5 | 0.2 | 0.3 | 3 | 3 | 0.76 | 3.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
6 | 2 | 0.2 | 0.3 | 8.5 | 8.5 | 0.76 | 9.26 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 1.5 | 0.625 | 0.2 | 0.5 | 0.35 | 3.175
2 | 0.875 | 0.2 | 0.3 | 3.375 | 3.375 | 0.76 | 4.135 | 12 | 3 | 0.2 | 0.3 | 15.5 | 12 | 3 | 0.2 | 0.5 | 15.7 | 8 | 3 | 0.2 | 0.5 | 0.35 | 12.05
1 | 0.5 | 0.2 | 0.3 | 2 | 2 | 0.76 | 2.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 0.75 | 0.5 | 0.2 | 0.5 | 0.35 | 2.3
0.75 | 0.5 | 0.2 | 0.3 | 1.75 | 1.75 | 0.76 | 2.51 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
0.75 | 0.5 | 0.2 | 0.3 | 1.75 | 1.75 | 0.76 | 2.51 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
6 | 2.5 | 0.2 | 0.3 | 9 | 9 | 0.76 | 9.76 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
2 | 0.5 | 0.2 | 0.3 | 3 | 3 | 0.76 | 3.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.25 | 0.5 | 0.2 | 0.5 | 0.35 | 2.8
2 | 0.5 | 0.2 | 0.3 | 3 | 3 | 0.76 | 3.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
2 | 0.75 | 0.2 | 0.3 | 3.25 | 3.25 | 0.76 | 4.01 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.75 | 0.25 | 0.2 | 0.5 | 0.35 | 2.05
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.25 | 0.5 | 0.2 | 0.5 | 0.35 | 2.8
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.25 | 0.5 | 0.2 | 0.5 | 0.35 | 2.8
1 | 0.5 | 0.2 | 0.3 | 2 | 2 | 0.76 | 2.76 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 2 | 1 | 0.2 | 0.5 | 0.35 | 4.05
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 1.25 | 0.625 | 0.2 | 0.5 | 0.35 | 2.925
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 0.75 | 0.1875 | 0.2 | 0.3 | 1.4375 | 0.75 | 0.1875 | 0.2 | 0.5 | 1.6375 | 0.5 | 0.1875 | 0.2 | 0.5 | 0.35 | 1.7375
0.75 | 0.5 | 0.2 | 0.3 | 1.75 | 1.75 | 0.76 | 2.51 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 1.75 | 0.75 | 0.2 | 0.5 | 0.35 | 3.55
1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 2.5 | 0.76 | 3.26 | 14 | 3.5 | 0.2 | 0.3 | 18 | 14 | 3.5 | 0.2 | 0.5 | 18.2 | 9 | 3.5 | 0.2 | 0.5 | 0.4 | 13.6
1.5 | 1 | 0.2 | 0.3 | 3 | 3 | 0.76 | 3.76 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 4 | 0.625 | 0.2 | 0.5 | 0.35 | 5.675
2 | 0.75 | 0.2 | 0.3 | 3.25 | 3.25 | 0.76 | 4.01 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
12 | 2.5 | 0.2 | 0.3 | 15 | 15 | 0.76 | 15.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
5 | 2 | 0.2 | 0.3 | 7.5 | 7.5 | 0.76 | 8.26 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 4 | 0.75 | 0.2 | 0.5 | 0.35 | 5.8
2 | 0.75 | 0.2 | 0.3 | 3.25 | 3.25 | 0.76 | 4.01 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
3 | 1 | 0.2 | 0.3 | 4.5 | 4.5 | 0.76 | 5.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
1 | 0.5 | 0.2 | 0.3 | 1 | 1 | 0.76 | 1.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
1 | 0.5 | 0.2 | 0.3 | 2 | 2 | 0.76 | 2.76 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 2.5 | 0.875 | 0.2 | 0.5 | 0.35 | 4.425
3 | 1 | 0.2 | 0.3 | 4.5 | 4.5 | 0.76 | 5.26 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 3 | 0.875 | 0.2 | 0.5 | 0.35 | 4.925
3 | 1.25 | 0.2 | 0.3 | 4.75 | 4.75 | 0.76 | 5.51 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 4 | 0.625 | 0.2 | 0.5 | 0.35 | 5.675
2 | 1 | 0.2 | 0.3 | 3.5 | 3.5 | 0.76 | 4.26 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 3 | 1 | 0.2 | 0.5 | 0.35 | 5.05
1.5 | 1.25 | 0.2 | 0.3 | 3.25 | 3.25 | 0.76 | 4.01 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 5 | 0.75 | 0.2 | 0.5 | 0.35 | 6.8
1.5 | 0.625 | 0.2 | 0.3 | 2.625 | 2.625 | 0.76 | 3.385 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 3 | 0.875 | 0.2 | 0.5 | 0.35 | 4.925
3.5 | 1.5 | 0.2 | 0.3 | 5.5 | 5.5 | 0.76 | 6.26 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
2 | 1 | 0.2 | 0.3 | 3.5 | 3.5 | 0.76 | 4.26 | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 2.75 | 0.875 | 0.2 | 0.5 | 0.35 | 4.675
1 | 0.5 | 0.2 | 0.3 | 2 | 2 | 0.76 | 2.76 | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
1.5 | 0.75 | 0.2 | 0.3 | 2.75 | 2.75 | 0.76 | 3.51 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 4 | 0.625 | 0.2 | 0.5 | 0.35 | 5.675
1.5 | 0.75 | 0.2 | 0.3 | 2.75 | 2.75 | 0.76 | 3.51 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 3.5 | 1 | 0.2 | 0.5 | 0.35 | 5.55
9.5 | 4.5 | 0.2 | 0.4 | 14.6 | 14.6 | 0.76 | 15.36 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.75 | 0.25 | 0.2 | 0.5 | 0.35 | 2.05
5 | 1.75 | 0.2 | 0.3 | 7.25 | 7.25 | 0.76 | 8.01 | 2.5 | 0.5 | 0.2 | 0.3 | 3.5 | 2.5 | 0.5 | 0.2 | 0.5 | 3.7 | 2 | 0.5 | 0.2 | 0.5 | 0.35 | 3.55
2 | 0.75 | 0.2 | 0.2 | 3.15 | 3.15 | 0.76 | 3.91 | 2.5 | 0.5 | 0.2 | 0.3 | 3.5 | 2.5 | 0.5 | 0.2 | 0.5 | 3.7 | 2 | 0.5 | 0.2 | 0.5 | 0.35 | 3.55
5 | 2.75 | 0.2 | 0.3 | 8.25 | 8.25 | 0.76 | 9.01 | 2.5 | 0.5 | 0.2 | 0.3 | 3.5 | 2.5 | 0.5 | 0.2 | 0.5 | 3.7 | 2 | 0.5 | 0.2 | 0.5 | 0.35 | 3.55
3 | 1.5 | 0.2 | 0.3 | 5 | 5 | 0.76 | 5.76 | 2.5 | 0.5 | 0.2 | 0.3 | 3.5 | 2.5 | 0.5 | 0.2 | 0.5 | 3.7 | 2 | 0.5 | 0.2 | 0.5 | 0.35 | 3.55
3.5 | 0.75 | 0.2 | 0.3 | 4.75 | 4.75 | 0.76 | 5.51 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 4 | 1 | 0.2 | 0.5 | 0.35 | 6.05
2.75 | 0.75 | 0.2 | 0.3 | 4 | 4 | 0.76 | 4.76 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 3.5 | 1 | 0.2 | 0.5 | 0.35 | 5.55
2.5 | 0.75 | 0.2 | 0.3 | 3.75 | 3.75 | 0.76 | 4.51 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
2.5 | 1 | 0.2 | 0.3 | 4 | 4 | 0.76 | 4.76 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
1.5 | 0.75 | 0.2 | 0.3 | 2.75 | 2.75 | 0.76 | 3.51 | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 1 | 0.625 | 0.2 | 0.5 | 0.35 | 2.675
2 | 1 | 0.2 | 0.3 | 3.5 | 3.5 | 0.76 | 4.26 | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 1 | 0.25 | 0.2 | 0.5 | 0.35 | 2.3
2.5 | 0.75 | 0.2 | 0.3 | 3.75 | 3.75 | 0.76 | 4.51 | 0.5 | 0.125 | 0.2 | 0.3 | 1.125 | 0.5 | 0.125 | 0.2 | 0.5 | 1.325 | 0.5 | 0.125 | 0.2 | 0.5 | 0.35 | 1.675
2 | 0.75 | 0.2 | 0.3 | 3.25 | 3.25 | 0.76 | 4.01 | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 4 | 1 | 0.2 | 0.5 | 0.35 | 6.05
2 | 1 | 0.2 | 0.3 | 3.5 | 3.5 | 0.76 | 4.26 | 0.75 | 0.1875 | 0.2 | 0.3 | 1.4375 | 0.75 | 0.1875 | 0.2 | 0.5 | 1.6375 | 0.5 | 0.1875 | 0.2 | 0.5 | 0.35 | 1.7375
2.5 | 1 | 0.2 | 0.3 | 4 | 4 | 0.76 | 4.76 | 0.75 | 0.1875 | 0.2 | 0.3 | 1.4375 | 0.75 | 0.1875 | 0.2 | 0.5 | 1.6375 | 0.5 | 0.1875 | 0.2 | 0.5 | 0.35 | 1.7375
192 | 69.5 | 14.2 | 21.3 | 297 |  | 53.96 | 350.96 | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[8 empty] | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
[8 empty] | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
[8 empty] | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
[8 empty] | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
[8 empty] | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
[8 empty] | 6 | 1.5 | 0.2 | 0.3 | 8 | 6 | 1.5 | 0.2 | 0.5 | 8.2 | 5 | 1.5 | 0.2 | 0.5 | 0.35 | 7.55
[8 empty] | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 4 | 1 | 0.2 | 0.5 | 0.35 | 6.05
[8 empty] | 1 | 0.25 | 0.2 | 0.3 | 1.75 | 1 | 0.25 | 0.2 | 0.5 | 1.95 | 0.5 | 0.25 | 0.2 | 0.5 | 0.35 | 1.8
[8 empty] | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 3.5 | 1 | 0.2 | 0.5 | 0.35 | 5.55
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 6 | 1.5 | 0.2 | 0.3 | 8 | 6 | 1.5 | 0.2 | 0.5 | 8.2 | 3 | 1.5 | 0.2 | 0.5 | 0.35 | 5.55
[8 empty] | 6 | 1.5 | 0.2 | 0.3 | 8 | 6 | 1.5 | 0.2 | 0.5 | 8.2 | 6 | 1.5 | 0.2 | 0.5 | 0.35 | 8.55
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
[8 empty] | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 1 | 0.375 | 0.2 | 0.5 | 0.35 | 2.425
[8 empty] | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 2 | 0.625 | 0.2 | 0.5 | 0.35 | 3.675
[8 empty] | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 3 | 0.875 | 0.2 | 0.5 | 0.35 | 4.925
[8 empty] | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 2 | 0.625 | 0.2 | 0.5 | 0.35 | 3.675
[8 empty] | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 2.75 | 0.875 | 0.2 | 0.5 | 0.35 | 4.675
[8 empty] | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 2.75 | 0.875 | 0.2 | 0.5 | 0.35 | 4.675
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 1.5 | 0.5 | 0.2 | 0.5 | 2.7 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[8 empty] | 1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 1.5 | 0.5 | 0.2 | 0.5 | 2.7 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1.5 | 0.5 | 0.2 | 0.5 | 0.35 | 3.05
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[8 empty] | 2 | 0.5 | 0.2 | 0.3 | 3 | 2 | 0.5 | 0.2 | 0.5 | 3.2 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2.5 | 0.75 | 0.2 | 0.5 | 0.35 | 4.3
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 1.5 | 0.75 | 0.2 | 0.5 | 0.35 | 3.3
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[8 empty] | 2.5 | 0.625 | 0.2 | 0.3 | 3.625 | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 2 | 0.625 | 0.2 | 0.5 | 0.35 | 3.675
[8 empty] | 1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 1.5 | 0.5 | 0.2 | 0.5 | 2.7 | 0.5 | 0.5 | 0.2 | 0.5 | 0.35 | 2.05
[8 empty] | 4 | 1 | 0.2 | 0.3 | 5.5 | 4 | 1 | 0.2 | 0.5 | 5.7 | 3 | 1 | 0.2 | 0.5 | 0.35 | 5.05
[8 empty] | 1.5 | 0.375 | 0.2 | 0.3 | 2.375 | 1.5 | 0.375 | 0.2 | 0.5 | 2.575 | 0.6 | 0.375 | 0.2 | 0.5 | 0.35 | 2.025
[8 empty] | 3.5 | 0.875 | 0.2 | 0.3 | 4.875 | 3.5 | 0.875 | 0.2 | 0.5 | 5.075 | 2 | 0.875 | 0.2 | 0.5 | 0.35 | 3.925
[8 empty] | 3 | 0.75 | 0.2 | 0.3 | 4.25 | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 1.5 | 0.75 | 0.2 | 0.5 | 0.35 | 3.3
[8 empty] | 1.5 | 0.5 | 0.2 | 0.3 | 2.5 | 1.5 | 0.5 | 0.2 | 0.5 | 2.7 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[8 empty] | 0.75 | 0.5 | 0.2 | 0.3 | 1.75 | 0.75 | 0.5 | 0.2 | 0.5 | 1.95 | 1 | 0.5 | 0.2 | 0.5 | 0.35 | 2.55
[13 empty] | 18 | 4.5 | 0.2 | 0.75 | 23.45 | 15 | 4.5 | 0.2 | 0.75 | 0.45 | 20.9
[13 empty] | 6 | 1.5 | 0.2 | 0.5 | 8.2 | 4 | 1.5 | 0.2 | 0.5 | 0.35 | 6.55
[13 empty] | 4 | 1 | 0.2 | 0.5 | 5.7 | 3 | 1 | 0.2 | 0.5 | 0.35 | 5.05
[13 empty] | 4 | 1 | 0.2 | 0.4 | 5.6 | 3 | 1 | 0.2 | 0.4 | 0.35 | 4.95
[13 empty] | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[13 empty] | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 2 | 0.75 | 0.2 | 0.5 | 0.35 | 3.8
[13 empty] | 3 | 0.75 | 0.2 | 0.5 | 4.45 | 0.75 | 0.75 | 0.2 | 0.5 | 0.35 | 2.55
[13 empty] | 2.5 | 0.625 | 0.2 | 0.5 | 3.825 | 1.25 | 0.625 | 0.2 | 0.5 | 0.35 | 2.925
[13 empty] | 15 | 3.75 | 0.2 | 0.8 | 19.75 | 12 | 3.75 | 0.2 | 0.8 | 0.45 | 17.2
[17 empty] | 556 | [5 empty] | 503