## Easicab_UIFunctionality_Review
Review Details Sprint No:
Project Name |  |  | Easi_Cab | [9 empty] | Reviewer Name | Subhalaxmi
Review Date |  |  | 2016-08-16 | [9 empty] | Review Item Author/s | Subhalaxmi,Nitesh
Phase of the Project |  |  | Phase 1 | [9 empty] | Project Phase Other Desc. | Phase 1
Review Item |  |  | UI/Functionalities of Android application | [9 empty] | Review Item Other Desc.
Reference Materials( SVN path ) |  |  | https://asi-storage07.blr.allegisindia.com/svn/EASi_App-POC/trunk/EasiCab/Documents/DesignDoc/DesignScreens | [9 empty] | Type of Review | Final Review
Defect Log
Sl.No - Initials of module | Location of Defect/ Revision | Line #/ Section # | Description of Defect | Type of defect | Priority | Assigned to | Status | Review Team Recommendation | SVN revision of the Created issue | SVN revision of Modified issue | SVN revision of Fixed | Actual Implementation/ Revision | Verified By | Verification Date
1 | Role.java review | Role page XML | UI: Customized the radio button and changes the color code of background and buttons | Ui Differ | Medium | Nitesh | Fixed | Improvement in UI | 40 | 46 | 50 | Verified | Subhalaxmi | 2016-08-17
Total Defects |  | 0

## Guidelines
Guidelines to use the Review Log Sheet
1 | Please ensure to fill in the "Review Details" at start of the review. "Phase of Project" should note the current phase the project is under e.g. Design, Coding, Review ,Testing.
2 | In case of document reviews, "Location of Defect" refers to combination of page number / paragraph / line number.
3 | In case of code reviews, "Location of Defect" refers to combination of module name. The Line #/ Section # should be used to specify line number in application .
4 | For the Sl.No. of the defect, use intials of module to identify the module for which the defect is raised eg. Sprint_1 - EasiCab,EasiCabUi&Funct,EasiCab_web etc
5 | A clear "Description of Defect" needs to be filled in and person responsible for addressing the issues is identified in the Assigned to column,
6 | The Status of error could be one of the following and to be set with consultation with the Moderator/ Reviewer.
|  | Open | Defect raised in the review
|  | Not a Defect | Analysis of defect indicated that it is not an Defect
|  | Fixed | Defect is fixed but pending verification from the Moderator/ Reviewer
|  | Verified | Defect has been verified to be fixed.
|  | Failed | Defect has failed Verification
7 | The Review Team Recommendation should be filled out in the Review Meeting and should be a description of the recommended change based on consensus or moderator direction.
8 | The Actual Implementation column should be filled in after the Assigned person has made changes to address the defect.
9 | The Verified By and Verification Date columns should be filled in after the items have been verified to be addressed.

## Easicab_web_Review
Review Details Sprint No:
Project Name | [12 empty] | Reviewer Name
Review Date | [12 empty] | Review Item Author/s
Phase of the Project | [12 empty] | Project Phase Other Desc.
Review Item | [12 empty] | Review Item Other Desc.
Reference Materials( SVN path ) | [12 empty] | Type of Review
Defect Log
Sl.No - Initials of module | Location of Defect/ Revision | Line #/ Section # | Description of Defect | Type of defect | Priority | Assigned to | Status | Review Team Recommendation | SVN revision of the Created issue | SVN revision of Modified issue | SVN revision of Fixed | Actual Implementation/ Revision | Verified By | Verification Date
Total Defects |  | 0